## Ribbon View
Fuse® Analyst Report
Workbook: Titan_II_Orbiter Baseline - 62 Activities
Schedule Quality
Created on: 6/2/2017
Created by: Neil
Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality
|  | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer
|  | 2018 | 2018 | 2019 | 2019 | 2020 | 2020 | 2021 | 2021 | Missing Logic | Logic Density™ | Critical | Hard Constraints | Negative Float | Insufficient Detail™ | Number of Lags | Number of Leads | Merge Hotspot | Score
Ribbons | Titan II Orbiter IMS | [8 empty] | 1 | 2.9 | 32 | 0 | 0 | 2 | 5 | 0 | 6 | 79
Ribbons | Titan II Orbiter IMS | [8 empty] | 2% |  | 53% | 0% | 0% | 5% | 8% | 0% | 10%
Phase Analyzer | Missing Logic | 1 | 5% | 0 | 0% | 0 | 0% | 0 | 0%
Phase Analyzer | Logic Density™ | 2.95 |  | 2.76 |  | 2.94 |  | 2.38
Phase Analyzer | Critical | 6 | 30% | 11 | 44% | 10 | 59% | 8 | 100%
Phase Analyzer | Hard Constraints | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Phase Analyzer | Negative Float | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Phase Analyzer | Insufficient Detail™ | 0 | 0% | 0 | 0% | 1 | 8% | 0 | 0%
Phase Analyzer | Number of Lags | 5 | 25% | 0 | 0% | 0 | 0% | 0 | 0%
Phase Analyzer | Number of Leads | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Phase Analyzer | Merge Hotspot | 1 | 5% | 3 | 18% | 2 | 13% | 0 | 0%
Phase Analyzer | Score | 68 |  | 70 |  | 83 |  | 100

## Ribbon Analysis
Fuse® Analyst Report
Workbook: Titan_II_Orbiter Baseline - 62 Activities
Schedule Quality
Created on: 6/2/2017
Created by: Neil
Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis
Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis
|  | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer
|  | Missing Logic | Logic Density™ | Critical | Hard Constraints | Negative Float | Insufficient Detail™ | Number of Lags | Number of Leads | Merge Hotspot | Score
Ribbons | Titan II Orbiter IMS | 1 | 2.9 | 32 | 0 | 0 | 2 | 5 | 0 | 6 | 79
Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis
|  | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer | Ribbon Analyzer
|  | Missing Logic | Logic Density™ | Critical | Hard Constraints | Negative Float | Insufficient Detail™ | Number of Lags | Number of Leads | Merge Hotspot | Score
Ribbons | Titan II Orbiter IMS | 2% |  | 53% | 0% | 0% | 5% | 8% | 0% | 10%

## Titan-II-Orbiter-IMS1
Fuse® Analyst Report
Workbook: Titan_II_Orbiter Baseline - 62 Activities
Schedule Quality
Created on: 6/2/2017
Created by: Neil
Titan II Orbiter IMS: Detailed View | Titan II Orbiter IMS: Detailed View | Titan II Orbiter IMS: Detailed View | Titan II Orbiter IMS: Detailed View | Titan II Orbiter IMS: Detailed View | Titan II Orbiter IMS: Detailed View
Missing Logic
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1245 | Program Start | Titan II Orbiter IMS | 0 | 0 | 2018-10-01 | 2018-10-01 | 0 |  |  | 0 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Start Milestone | TRUE | 2018-10-01 | 2018-10-01 | FALSE | TRUE | None |  | None | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.1 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
Critical
Number of critical activities
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1245 | Program Start | Titan II Orbiter IMS | 0 | 0 | 2018-10-01 | 2018-10-01 | 0 |  |  | 0 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Start Milestone | TRUE | 2018-10-01 | 2018-10-01 | FALSE | TRUE | None |  | None | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.1 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1000 | Receive Final Concept Design | Titan II Orbiter IMS | 1 | 1 | 2018-10-01 | 2018-10-01 | 0 |  |  | 0 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2144 | 2144 | 0 | 2144 | 2144 | 2 | FALSE | Normal | TRUE | 2018-10-01 | 2018-10-01 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Planned | 0% | 48 | 0 | 48 | 48 | Titan II Orbiter IMS.1.1.2.1.2.1.1.2.1.1 | Engineering Design | 0 | 0 | 0 | 0 | 0 | 2144 | PercentComplete | 6% | CP_Phys | 0/100 | Hamilton | Design
FALSE |  | A1010 | Final Design Review | Titan II Orbiter IMS | 5 | 5 | 2018-10-01 | 2018-10-05 | 0 |  |  | 0 | 2018-10-01 | 2018-10-05 | 2018-10-01 | 2018-10-05 | 10720 | 10720 | 0 | 10720 | 10720 | 2 | FALSE | Normal | TRUE | 2018-10-01 | 2018-10-05 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 240 | 0 | 240 | 240 | Titan II Orbiter IMS.1.1.2.1.2.1.1.2.1.1 | Engineering Design | 0 | 0 | 0 | 0 | 0 | 10720 | PercentComplete | 6% | CP_Phys | 0/100 | Hamilton | Design
FALSE |  | A1020 | Final Drawings Review | Titan II Orbiter IMS | 5 | 5 | 2018-10-01 | 2018-10-05 | 0 |  |  | 0 | 2018-10-01 | 2018-10-05 | 2018-10-01 | 2018-10-05 | 8320 | 8320 | 0 | 8320 | 8320 | 1 | FALSE | Normal | TRUE | 2018-10-01 | 2018-10-05 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 200 | 0 | 200 | 200 | Titan II Orbiter IMS.1.1.2.1.2.1.1.2.1.1 | Engineering Design | 0 | 0 | 0 | 0 | 0 | 8320 | PercentComplete | 6% | CP_Phys | 0/100 | Hamilton | Design
FALSE |  | A1030 | Design Complete | Titan II Orbiter IMS | 0 | 0 | 2018-10-05 | 2018-10-05 | 0 |  |  | 0 | 2018-10-05 | 2018-10-05 | 2018-10-05 | 2018-10-05 | 0 | 0 | 0 | 0 | 0 | 10 | FALSE | Finish Milestone | TRUE | 2018-10-05 | 2018-10-05 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 0 | 3 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 60 | 5 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.1.1.2.1.1 | Engineering Design | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1560 | Acquire Laptop Computers | Titan II Orbiter IMS | 90 | 90 | 2018-10-08 | 2019-02-08 | 0 |  |  | 0 | 2018-10-08 | 2019-02-08 | 2018-10-08 | 2019-02-08 | 216999.98 | 216999.98 | 0 | 216999.98 | 216999.98 | 1 | FALSE | Normal | TRUE | 2018-10-08 | 2019-02-08 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 216999.98 | PercentComplete | 6% | CP_Phys | Units Complete | Lincoln | Procurement
FALSE |  | A1570 | Acquire Cabling | Titan II Orbiter IMS | 67 | 67 | 2019-02-11 | 2019-05-14 | 0 |  |  | 0 | 2019-02-11 | 2019-05-14 | 2019-02-11 | 2019-05-14 | 3000 | 3000 | 0 | 2999.9997 | 2999.9997 | 1 | FALSE | Normal | TRUE | 2019-02-11 | 2019-05-14 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 67 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 3000 | PercentComplete | 6% | CP_Phys | Units Complete | Lincoln | Procurement
FALSE |  | A1580 | Assemble and Install Software | Titan II Orbiter IMS | 45 | 45 | 2019-05-15 | 2019-07-16 | 0 |  |  | 0 | 2019-05-15 | 2019-07-16 | 2019-05-15 | 2019-07-16 | 63000 | 63000 | 0 | 63000 | 63000 | 1 | FALSE | Normal | TRUE | 2019-05-15 | 2019-07-16 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 45 | 0 |  | Planned | 0% | 1800 | 0 | 1800 | 1800 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 63000 | PercentComplete | 6% | CP_Phys | Units Complete | Lincoln | Procurement
FALSE |  | A1600 | Procurement Complete | Titan II Orbiter IMS | 0 | 0 | 2019-07-16 | 2019-07-16 | 0 |  |  | 0 | 2019-07-16 | 2019-07-16 | 2019-07-16 | 2019-07-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-07-16 | 2019-07-16 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1150 | Clean Room Assembly Start | Titan II Orbiter IMS | 0 | 0 | 2019-07-17 | 2019-07-17 | 0 |  |  | 0 | 2019-07-17 | 2019-07-17 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Start Milestone | TRUE | 2019-07-17 | 2019-07-17 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.2 | Clean Room Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1160 | Move to Clean Room | Titan II Orbiter IMS | 5 | 5 | 2019-07-17 | 2019-07-23 | 0 |  |  | 0 | 2019-07-17 | 2019-07-23 | 2019-07-17 | 2019-07-23 | 4200 | 4200 | 0 | 4200 | 4200 | 3 | FALSE | Normal | TRUE | 2019-07-17 | 2019-07-23 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 120 | 0 | 120 | 120 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.2 | Clean Room Assembly | 0 | 0 | 0 | 0 | 0 | 4200 | PercentComplete | 6% | CP_Phys | 0/100 |  | Engineering
FALSE |  | A1190 | Install Special Sensors | Titan II Orbiter IMS | 23 | 23 | 2019-07-24 | 2019-08-23 | 0 |  |  | 0 | 2019-07-24 | 2019-08-23 | 2019-07-24 | 2019-08-23 | 106480 | 106480 | 0 | 106480 | 106480 | 1 | FALSE | Normal | TRUE | 2019-07-24 | 2019-08-23 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 23 | 0 |  | Planned | 0% | 920 | 0 | 920 | 920 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.2 | Clean Room Assembly | 0 | 0 | 0 | 0 | 0 | 106480 | PercentComplete | 6% | CP_Phys | Percent Complete |  | Engineering
FALSE |  | A1200 | Install Dish and Telemetry Systems | Titan II Orbiter IMS | 14 | 14 | 2019-08-26 | 2019-09-12 | 0 |  |  | 0 | 2019-08-26 | 2019-09-12 | 2019-08-26 | 2019-09-12 | 55440 | 55440 | 0 | 55440 | 55440 | 1 | FALSE | Normal | TRUE | 2019-08-26 | 2019-09-12 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 14 | 0 |  | Planned | 0% | 336 | 0 | 336 | 336 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.2 | Clean Room Assembly | 0 | 0 | 0 | 0 | 0 | 55440 | PercentComplete | 6% | CP_Phys | Percent Complete |  | Engineering
FALSE |  | A1210 | Install Computer Boards | Titan II Orbiter IMS | 15 | 15 | 2019-09-13 | 2019-10-03 | 0 |  |  | 0 | 2019-09-13 | 2019-10-03 | 2019-09-13 | 2019-10-03 | 8400 | 8400 | 0 | 8400 | 8400 | 1 | FALSE | Normal | TRUE | 2019-09-13 | 2019-10-03 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 0 |  | Planned | 0% | 240 | 0 | 240 | 240 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.2 | Clean Room Assembly | 0 | 0 | 0 | 0 | 0 | 8400 | PercentComplete | 6% | CP_Phys | Percent Complete |  | Engineering
FALSE |  | A1220 | Install Guidance System Electronics | Titan II Orbiter IMS | 34 | 34 | 2019-10-04 | 2019-11-20 | 0 |  |  | 0 | 2019-10-04 | 2019-11-20 | 2019-10-04 | 2019-11-20 | 78120 | 78120 | 0 | 78120 | 78120 | 1 | FALSE | Normal | TRUE | 2019-10-04 | 2019-11-20 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 34 | 0 |  | Planned | 0% | 1360 | 0 | 1360 | 1360 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.2 | Clean Room Assembly | 0 | 0 | 0 | 0 | 0 | 78120 | PercentComplete | 6% | CP_Phys | Percent Complete |  | Engineering
FALSE |  | A1230 | Install Final Exterior Casing Assembly | Titan II Orbiter IMS | 31 | 31 | 2019-11-21 | 2020-01-02 | 0 |  |  | 0 | 2019-11-21 | 2020-01-02 | 2019-11-21 | 2020-01-02 | 19600 | 19600 | 0 | 19600 | 19600 | 1 | FALSE | Normal | TRUE | 2019-11-21 | 2020-01-02 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 31 | 0 |  | Planned | 0% | 496 | 0 | 496 | 496 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.2 | Clean Room Assembly | 0 | 0 | 0 | 0 | 0 | 19600 | PercentComplete | 6% | CP_Phys | Percent Complete |  | Engineering
FALSE |  | A1240 | Clean Room Assembly Complete | Titan II Orbiter IMS | 0 | 0 | 2020-01-03 | 2020-01-03 | 0 |  |  | 0 | 2020-01-03 | 2020-01-03 | 2020-01-03 | 2020-01-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Start Milestone | TRUE | 2020-01-03 | 2020-01-03 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.2 | Clean Room Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1260 | Test Start | Titan II Orbiter IMS | 0 | 0 | 2020-01-03 | 2020-01-03 | 0 |  |  | 0 | 2020-01-03 | 2020-01-03 | 2020-01-03 | 2020-01-03 | 0 | 0 | 0 | 0 | 0 | 6 | FALSE | Start Milestone | TRUE | 2020-01-03 | 2020-01-03 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.3 | Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1270 | Hydrazine Testing | Titan II Orbiter IMS | 180 | 180 | 2020-01-03 | 2020-09-10 | 0 |  |  | 0 | 2020-01-03 | 2020-09-10 | 2020-01-03 | 2020-09-10 | 74880 | 74880 | 0 | 74880 | 74880 | 2 | FALSE | Normal | TRUE | 2020-01-03 | 2020-09-10 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 180 | 0 |  | Planned | 0% | 1440 | 0 | 1440 | 1440 | Titan II Orbiter IMS.1.1.2.1.2.3 | Test | 0 | 0 | 0 | 0 | 0 | 74880 | PercentComplete | 6% | CP_Phys | Percent Complete |  | Space Team
FALSE |  | A1340 | Test Complete | Titan II Orbiter IMS | 0 | 0 | 2020-09-11 | 2020-09-11 | 0 |  |  | 0 | 2020-09-11 | 2020-09-11 | 2020-09-11 | 2020-09-11 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Start Milestone | TRUE | 2020-09-11 | 2020-09-11 | FALSE | TRUE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.3 | Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1360 | Launch Preparation Start | Titan II Orbiter IMS | 0 | 0 | 2020-09-11 | 2020-09-11 | 0 |  |  | 0 | 2020-09-11 | 2020-09-11 | 2020-09-11 | 2020-09-11 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Start Milestone | TRUE | 2020-09-11 | 2020-09-11 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.4 | Launch Preparation | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1370 | Drop | Titan II Orbiter IMS | 20 | 20 | 2020-09-11 | 2020-10-08 | 0 |  |  | 0 | 2020-09-11 | 2020-10-08 | 2020-09-11 | 2020-10-08 | 36320 | 36320 | 0 | 36320 | 36320 | 1 | FALSE | Normal | TRUE | 2020-09-11 | 2020-10-08 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 800 | 0 | 800 | 800 | Titan II Orbiter IMS.1.1.2.1.2.4.1.2.4.2 | Stress Tests | 0 | 0 | 0 | 0 | 0 | 36320 | PercentComplete | 6% | CP_Phys | 50/50 | Lincoln | Space Team
FALSE |  | A1380 | G-Force | Titan II Orbiter IMS | 20 | 20 | 2020-10-09 | 2020-11-05 | 0 |  |  | 0 | 2020-10-09 | 2020-11-05 | 2020-10-09 | 2020-11-05 | 30720 | 30720 | 0 | 30720 | 30720 | 1 | FALSE | Normal | TRUE | 2020-10-09 | 2020-11-05 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 640 | 0 | 640 | 640 | Titan II Orbiter IMS.1.1.2.1.2.4.1.2.4.2 | Stress Tests | 0 | 0 | 0 | 0 | 0 | 30720 | PercentComplete | 6% | CP_Phys | 50/50 | Lincoln | Space Team
FALSE |  | A1390 | Vibration | Titan II Orbiter IMS | 39 | 39 | 2020-11-06 | 2020-12-30 | 0 |  |  | 0 | 2020-11-06 | 2020-12-30 | 2020-11-06 | 2020-12-30 | 36320 | 36320 | 0 | 36320 | 36320 | 1 | FALSE | Normal | TRUE | 2020-11-06 | 2020-12-30 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 39 | 0 |  | Planned | 0% | 800 | 0 | 800 | 800 | Titan II Orbiter IMS.1.1.2.1.2.4.1.2.4.2 | Stress Tests | 0 | 0 | 0 | 0 | 0 | 36320 | PercentComplete | 6% | CP_Phys | Percent Complete | Lincoln | Space Team
FALSE |  | A1400 | Final Inspections | Titan II Orbiter IMS | 20 | 20 | 2020-12-31 | 2021-01-27 | 0 |  |  | 0 | 2020-12-31 | 2021-01-27 | 2020-12-31 | 2021-01-27 | 34720 | 34720 | 0 | 34720 | 34720 | 2 | FALSE | Normal | TRUE | 2020-12-31 | 2021-01-27 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 800 | 0 | 800 | 800 | Titan II Orbiter IMS.1.1.2.1.2.4 | Launch Preparation | 0 | 0 | 0 | 0 | 0 | 34720 | PercentComplete | 6% | CP_Phys | 50/50 | Lincoln | Space Team
FALSE |  | A1410 | Clean and Seal for Payload | Titan II Orbiter IMS | 20 | 20 | 2021-01-28 | 2021-02-24 | 0 |  |  | 0 | 2021-01-28 | 2021-02-24 | 2021-01-28 | 2021-02-24 | 19520 | 19520 | 0 | 19520 | 19520 | 1 | FALSE | Normal | TRUE | 2021-01-28 | 2021-02-24 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 480 | 0 | 480 | 480 | Titan II Orbiter IMS.1.1.2.1.2.4 | Launch Preparation | 0 | 0 | 0 | 0 | 0 | 19520 | PercentComplete | 6% | CP_Phys | 50/50 | Lincoln | Space Team
FALSE |  | A1420 | Launch Preparation Complete | Titan II Orbiter IMS | 0 | 0 | 2021-02-25 | 2021-02-25 | 0 |  |  | 0 | 2021-02-25 | 2021-02-25 | 2021-02-25 | 2021-02-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Start Milestone | TRUE | 2021-02-25 | 2021-02-25 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.4 | Launch Preparation | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1440 | Deploy to Launch Facility | Titan II Orbiter IMS | 20 | 20 | 2021-02-25 | 2021-03-24 | 0 |  |  | 0 | 2021-02-25 | 2021-03-24 | 2021-02-25 | 2021-03-24 | 14080 | 14080 | 0 | 14080 | 14080 | 1 | FALSE | Normal | TRUE | 2021-02-25 | 2021-03-24 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 320 | 0 | 320 | 320 | Titan II Orbiter IMS.1.1.2.1.2.5 | Launch | 0 | 0 | 0 | 0 | 0 | 14080 | PercentComplete | 6% | CP_Phys | 50/50 | Lincoln | Space Team
FALSE |  | A1450 | Mount in Atlas V Payload Capsule | Titan II Orbiter IMS | 18 | 18 | 2021-03-25 | 2021-04-19 | 0 |  |  | 0 | 2021-03-25 | 2021-04-19 | 2021-03-25 | 2021-04-19 | 91440 | 91440 | 0 | 91440 | 91440 | 1 | FALSE | Normal | TRUE | 2021-03-25 | 2021-04-19 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 18 | 0 |  | Planned | 0% | 2016 | 0 | 2016 | 2016 | Titan II Orbiter IMS.1.1.2.1.2.5 | Launch | 0 | 0 | 0 | 0 | 0 | 91440 | PercentComplete | 6% | CP_Phys | 50/50 | Lincoln | Space Team
FALSE |  | A1430 | Program Management Complete | Titan II Orbiter IMS | 0 | 0 | 2021-04-20 | 2021-04-20 | 0 |  |  | 0 | 2021-04-20 | 2021-04-20 | 2021-04-19 | 2021-04-19 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | TRUE | 2021-04-20 | 2021-04-20 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.1 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1460 | Atlas V Deployed to Launch Site | Titan II Orbiter IMS | 0 | 0 | 2021-04-20 | 2021-04-20 | 0 |  |  | 0 | 2021-04-20 | 2021-04-20 | 2021-04-19 | 2021-04-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Start Milestone | TRUE | 2021-04-20 | 2021-04-20 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.5 | Launch | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1470 | LAUNCH | Titan II Orbiter IMS | 0 | 0 | 2021-04-20 | 2021-04-20 | 0 |  |  | 0 | 2021-04-20 | 2021-04-20 | 2021-04-19 | 2021-04-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Start Milestone | TRUE | 2021-04-20 | 2021-04-20 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.5 | Launch | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
Insufficient Detail™
Number of activities that have a duration longer than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1530 | RF Sensor | Titan II Orbiter IMS | 150 | 150 | 2018-12-17 | 2019-07-12 | 2 |  |  | 0 | 2018-12-17 | 2019-07-12 | 2018-12-19 | 2019-07-16 | 2 | 2 | 0 | 1200 | 1200 | 1 | FALSE | Normal | FALSE | 2018-12-17 | 2019-07-12 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 150 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 1200 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1270 | Hydrazine Testing | Titan II Orbiter IMS | 180 | 180 | 2020-01-03 | 2020-09-10 | 0 |  |  | 0 | 2020-01-03 | 2020-09-10 | 2020-01-03 | 2020-09-10 | 74880 | 74880 | 0 | 74880 | 74880 | 2 | FALSE | Normal | TRUE | 2020-01-03 | 2020-09-10 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 180 | 0 |  | Planned | 0% | 1440 | 0 | 1440 | 1440 | Titan II Orbiter IMS.1.1.2.1.2.3 | Test | 0 | 0 | 0 | 0 | 0 | 74880 | PercentComplete | 6% | CP_Phys | Percent Complete |  | Space Team
Number of Lags
Total number of activities that have lags in their predecessors. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1500 | Electromagnetic Sensor | Titan II Orbiter IMS | 90 | 90 | 2018-10-22 | 2019-02-22 | 102 |  |  | 100 | 2018-10-22 | 2019-02-22 | 2019-03-13 | 2019-07-16 | 170000 | 170000 | 0 | 170000 | 170000 | 1 | FALSE | Normal | FALSE | 2018-10-22 | 2019-02-22 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 170000 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1510 | Ultraviolet Sensor | Titan II Orbiter IMS | 67 | 67 | 2018-11-05 | 2019-02-05 | 115 |  |  | 113 | 2018-11-05 | 2019-02-05 | 2019-04-15 | 2019-07-16 | 140000 | 140000 | 0 | 140000 | 140000 | 1 | FALSE | Normal | FALSE | 2018-11-05 | 2019-02-05 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 67 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 140000 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1520 | Infrared Sensor | Titan II Orbiter IMS | 66 | 66 | 2018-11-19 | 2019-02-18 | 106 |  |  | 104 | 2018-11-19 | 2019-02-18 | 2019-04-16 | 2019-07-16 | 135000 | 135000 | 0 | 135000 | 135000 | 1 | FALSE | Normal | FALSE | 2018-11-19 | 2019-02-18 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 66 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 135000 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1530 | RF Sensor | Titan II Orbiter IMS | 150 | 150 | 2018-12-17 | 2019-07-12 | 2 |  |  | 0 | 2018-12-17 | 2019-07-12 | 2018-12-19 | 2019-07-16 | 2 | 2 | 0 | 1200 | 1200 | 1 | FALSE | Normal | FALSE | 2018-12-17 | 2019-07-12 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 150 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 1200 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1540 | Stereoscopic Camera | Titan II Orbiter IMS | 90 | 90 | 2018-12-31 | 2019-05-03 | 52 |  |  | 50 | 2018-12-31 | 2019-05-03 | 2019-03-13 | 2019-07-16 | 1 | 1 | 0 | 720 | 720 | 1 | FALSE | Normal | FALSE | 2018-12-31 | 2019-05-03 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 720 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
Merge Hotspot
The total number of activities with a high number of predecessor links.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1030 | Design Complete | Titan II Orbiter IMS | 0 | 0 | 2018-10-05 | 2018-10-05 | 0 |  |  | 0 | 2018-10-05 | 2018-10-05 | 2018-10-05 | 2018-10-05 | 0 | 0 | 0 | 0 | 0 | 10 | FALSE | Finish Milestone | TRUE | 2018-10-05 | 2018-10-05 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 0 | 3 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 60 | 5 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.1.1.2.1.1 | Engineering Design | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1140 | Workshop Assembly Complete | Titan II Orbiter IMS | 0 | 0 | 2019-05-02 | 2019-05-02 | 54 |  |  | 54 | 2019-05-02 | 2019-05-02 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Start Milestone | FALSE | 2019-05-02 | 2019-05-02 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.1 | Workshop Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1550 | Instrument Procurement Complete | Titan II Orbiter IMS | 0 | 0 | 2019-07-12 | 2019-07-12 | 2 |  |  | 2 | 2019-07-12 | 2019-07-12 | 2019-07-16 | 2019-07-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-07-12 | 2019-07-12 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1600 | Procurement Complete | Titan II Orbiter IMS | 0 | 0 | 2019-07-16 | 2019-07-16 | 0 |  |  | 0 | 2019-07-16 | 2019-07-16 | 2019-07-16 | 2019-07-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-07-16 | 2019-07-16 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1240 | Clean Room Assembly Complete | Titan II Orbiter IMS | 0 | 0 | 2020-01-03 | 2020-01-03 | 0 |  |  | 0 | 2020-01-03 | 2020-01-03 | 2020-01-03 | 2020-01-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Start Milestone | TRUE | 2020-01-03 | 2020-01-03 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.2 | Clean Room Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1340 | Test Complete | Titan II Orbiter IMS | 0 | 0 | 2020-09-11 | 2020-09-11 | 0 |  |  | 0 | 2020-09-11 | 2020-09-11 | 2020-09-11 | 2020-09-11 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Start Milestone | TRUE | 2020-09-11 | 2020-09-11 | FALSE | TRUE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.3 | Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys

## Phase Analysis
Fuse® Analyst Report
Workbook: Titan_II_Orbiter Baseline - 62 Activities
Schedule Quality
Created on: 6/2/2017
Created by: Neil
Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis
Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis
|  | Time Line | Time Line | Time Line | Time Line
|  | 2018 | 2019 | 2020 | 2021
Phase Analyzer | Missing Logic | 1 | 0 | 0 | 0
Phase Analyzer | Logic Density™ | 2.95 | 2.76 | 2.94 | 2.38
Phase Analyzer | Critical | 6 | 11 | 10 | 8
Phase Analyzer | Hard Constraints | 0 | 0 | 0 | 0
Phase Analyzer | Negative Float | 0 | 0 | 0 | 0
Phase Analyzer | Insufficient Detail™ | 0 | 0 | 1 | 0
Phase Analyzer | Number of Lags | 5 | 0 | 0 | 0
Phase Analyzer | Number of Leads | 0 | 0 | 0 | 0
Phase Analyzer | Merge Hotspot | 1 | 3 | 2 | 0
Phase Analyzer | Score | 68 | 70 | 83 | 100
Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis
|  | Time Line | Time Line | Time Line | Time Line
|  | 2018 | 2019 | 2020 | 2021
Phase Analyzer | Missing Logic | 5% | 0% | 0% | 0%
Phase Analyzer | Logic Density™
Phase Analyzer | Critical | 30% | 44% | 59% | 100%
Phase Analyzer | Hard Constraints | 0% | 0% | 0% | 0%
Phase Analyzer | Negative Float | 0% | 0% | 0% | 0%
Phase Analyzer | Insufficient Detail™ | 0% | 0% | 8% | 0%
Phase Analyzer | Number of Lags | 25% | 0% | 0% | 0%
Phase Analyzer | Number of Leads | 0% | 0% | 0% | 0%
Phase Analyzer | Merge Hotspot | 5% | 18% | 13% | 0%
Phase Analyzer | Score

## 2018 Details
Fuse® Analyst Report
Workbook: Titan_II_Orbiter Baseline - 62 Activities
Schedule Quality
Created on: 6/2/2017
Created by: Neil
2018: Detailed View | 2018: Detailed View | 2018: Detailed View | 2018: Detailed View | 2018: Detailed View
Missing Logic
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1245 | Program Start | Titan II Orbiter IMS | 0 | 0 | 2018-10-01 | 2018-10-01 | 0 |  |  | 0 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Start Milestone | TRUE | 2018-10-01 | 2018-10-01 | FALSE | TRUE | None |  | None | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.1 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
Critical
Number of critical activities
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1245 | Program Start | Titan II Orbiter IMS | 0 | 0 | 2018-10-01 | 2018-10-01 | 0 |  |  | 0 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Start Milestone | TRUE | 2018-10-01 | 2018-10-01 | FALSE | TRUE | None |  | None | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.1 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1000 | Receive Final Concept Design | Titan II Orbiter IMS | 1 | 1 | 2018-10-01 | 2018-10-01 | 0 |  |  | 0 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2144 | 2144 | 0 | 2144 | 2144 | 2 | FALSE | Normal | TRUE | 2018-10-01 | 2018-10-01 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Planned | 0% | 48 | 0 | 48 | 48 | Titan II Orbiter IMS.1.1.2.1.2.1.1.2.1.1 | Engineering Design | 0 | 0 | 0 | 0 | 0 | 2144 | PercentComplete | 6% | CP_Phys | 0/100 | Hamilton | Design
FALSE |  | A1010 | Final Design Review | Titan II Orbiter IMS | 5 | 5 | 2018-10-01 | 2018-10-05 | 0 |  |  | 0 | 2018-10-01 | 2018-10-05 | 2018-10-01 | 2018-10-05 | 10720 | 10720 | 0 | 10720 | 10720 | 2 | FALSE | Normal | TRUE | 2018-10-01 | 2018-10-05 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 240 | 0 | 240 | 240 | Titan II Orbiter IMS.1.1.2.1.2.1.1.2.1.1 | Engineering Design | 0 | 0 | 0 | 0 | 0 | 10720 | PercentComplete | 6% | CP_Phys | 0/100 | Hamilton | Design
FALSE |  | A1020 | Final Drawings Review | Titan II Orbiter IMS | 5 | 5 | 2018-10-01 | 2018-10-05 | 0 |  |  | 0 | 2018-10-01 | 2018-10-05 | 2018-10-01 | 2018-10-05 | 8320 | 8320 | 0 | 8320 | 8320 | 1 | FALSE | Normal | TRUE | 2018-10-01 | 2018-10-05 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 200 | 0 | 200 | 200 | Titan II Orbiter IMS.1.1.2.1.2.1.1.2.1.1 | Engineering Design | 0 | 0 | 0 | 0 | 0 | 8320 | PercentComplete | 6% | CP_Phys | 0/100 | Hamilton | Design
FALSE |  | A1030 | Design Complete | Titan II Orbiter IMS | 0 | 0 | 2018-10-05 | 2018-10-05 | 0 |  |  | 0 | 2018-10-05 | 2018-10-05 | 2018-10-05 | 2018-10-05 | 0 | 0 | 0 | 0 | 0 | 10 | FALSE | Finish Milestone | TRUE | 2018-10-05 | 2018-10-05 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 0 | 3 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 60 | 5 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.1.1.2.1.1 | Engineering Design | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1560 | Acquire Laptop Computers | Titan II Orbiter IMS | 90 | 90 | 2018-10-08 | 2019-02-08 | 0 |  |  | 0 | 2018-10-08 | 2019-02-08 | 2018-10-08 | 2019-02-08 | 216999.98 | 216999.98 | 0 | 216999.98 | 216999.98 | 1 | FALSE | Normal | TRUE | 2018-10-08 | 2019-02-08 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 216999.98 | PercentComplete | 6% | CP_Phys | Units Complete | Lincoln | Procurement
Number of Lags
Total number of activities that have lags in their predecessors. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1500 | Electromagnetic Sensor | Titan II Orbiter IMS | 90 | 90 | 2018-10-22 | 2019-02-22 | 102 |  |  | 100 | 2018-10-22 | 2019-02-22 | 2019-03-13 | 2019-07-16 | 170000 | 170000 | 0 | 170000 | 170000 | 1 | FALSE | Normal | FALSE | 2018-10-22 | 2019-02-22 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 170000 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1510 | Ultraviolet Sensor | Titan II Orbiter IMS | 67 | 67 | 2018-11-05 | 2019-02-05 | 115 |  |  | 113 | 2018-11-05 | 2019-02-05 | 2019-04-15 | 2019-07-16 | 140000 | 140000 | 0 | 140000 | 140000 | 1 | FALSE | Normal | FALSE | 2018-11-05 | 2019-02-05 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 67 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 140000 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1520 | Infrared Sensor | Titan II Orbiter IMS | 66 | 66 | 2018-11-19 | 2019-02-18 | 106 |  |  | 104 | 2018-11-19 | 2019-02-18 | 2019-04-16 | 2019-07-16 | 135000 | 135000 | 0 | 135000 | 135000 | 1 | FALSE | Normal | FALSE | 2018-11-19 | 2019-02-18 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 66 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 135000 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1530 | RF Sensor | Titan II Orbiter IMS | 150 | 150 | 2018-12-17 | 2019-07-12 | 2 |  |  | 0 | 2018-12-17 | 2019-07-12 | 2018-12-19 | 2019-07-16 | 2 | 2 | 0 | 1200 | 1200 | 1 | FALSE | Normal | FALSE | 2018-12-17 | 2019-07-12 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 150 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 1200 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1540 | Stereoscopic Camera | Titan II Orbiter IMS | 90 | 90 | 2018-12-31 | 2019-05-03 | 52 |  |  | 50 | 2018-12-31 | 2019-05-03 | 2019-03-13 | 2019-07-16 | 1 | 1 | 0 | 720 | 720 | 1 | FALSE | Normal | FALSE | 2018-12-31 | 2019-05-03 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 720 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
Merge Hotspot
The total number of activities with a high number of predecessor links.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1030 | Design Complete | Titan II Orbiter IMS | 0 | 0 | 2018-10-05 | 2018-10-05 | 0 |  |  | 0 | 2018-10-05 | 2018-10-05 | 2018-10-05 | 2018-10-05 | 0 | 0 | 0 | 0 | 0 | 10 | FALSE | Finish Milestone | TRUE | 2018-10-05 | 2018-10-05 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 0 | 3 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 60 | 5 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.1.1.2.1.1 | Engineering Design | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys

## 2019 Details
Fuse® Analyst Report
Workbook: Titan_II_Orbiter Baseline - 62 Activities
Schedule Quality
Created on: 6/2/2017
Created by: Neil
2019: Detailed View | 2019: Detailed View | 2019: Detailed View
Critical
Number of critical activities
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1560 | Acquire Laptop Computers | Titan II Orbiter IMS | 90 | 90 | 2018-10-08 | 2019-02-08 | 0 |  |  | 0 | 2018-10-08 | 2019-02-08 | 2018-10-08 | 2019-02-08 | 216999.98 | 216999.98 | 0 | 216999.98 | 216999.98 | 1 | FALSE | Normal | TRUE | 2018-10-08 | 2019-02-08 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 216999.98 | PercentComplete | 6% | CP_Phys | Units Complete | Lincoln | Procurement
FALSE |  | A1570 | Acquire Cabling | Titan II Orbiter IMS | 67 | 67 | 2019-02-11 | 2019-05-14 | 0 |  |  | 0 | 2019-02-11 | 2019-05-14 | 2019-02-11 | 2019-05-14 | 3000 | 3000 | 0 | 2999.9997 | 2999.9997 | 1 | FALSE | Normal | TRUE | 2019-02-11 | 2019-05-14 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 67 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 3000 | PercentComplete | 6% | CP_Phys | Units Complete | Lincoln | Procurement
FALSE |  | A1580 | Assemble and Install Software | Titan II Orbiter IMS | 45 | 45 | 2019-05-15 | 2019-07-16 | 0 |  |  | 0 | 2019-05-15 | 2019-07-16 | 2019-05-15 | 2019-07-16 | 63000 | 63000 | 0 | 63000 | 63000 | 1 | FALSE | Normal | TRUE | 2019-05-15 | 2019-07-16 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 45 | 0 |  | Planned | 0% | 1800 | 0 | 1800 | 1800 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 63000 | PercentComplete | 6% | CP_Phys | Units Complete | Lincoln | Procurement
FALSE |  | A1600 | Procurement Complete | Titan II Orbiter IMS | 0 | 0 | 2019-07-16 | 2019-07-16 | 0 |  |  | 0 | 2019-07-16 | 2019-07-16 | 2019-07-16 | 2019-07-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-07-16 | 2019-07-16 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1150 | Clean Room Assembly Start | Titan II Orbiter IMS | 0 | 0 | 2019-07-17 | 2019-07-17 | 0 |  |  | 0 | 2019-07-17 | 2019-07-17 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Start Milestone | TRUE | 2019-07-17 | 2019-07-17 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.2 | Clean Room Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1160 | Move to Clean Room | Titan II Orbiter IMS | 5 | 5 | 2019-07-17 | 2019-07-23 | 0 |  |  | 0 | 2019-07-17 | 2019-07-23 | 2019-07-17 | 2019-07-23 | 4200 | 4200 | 0 | 4200 | 4200 | 3 | FALSE | Normal | TRUE | 2019-07-17 | 2019-07-23 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 120 | 0 | 120 | 120 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.2 | Clean Room Assembly | 0 | 0 | 0 | 0 | 0 | 4200 | PercentComplete | 6% | CP_Phys | 0/100 |  | Engineering
FALSE |  | A1190 | Install Special Sensors | Titan II Orbiter IMS | 23 | 23 | 2019-07-24 | 2019-08-23 | 0 |  |  | 0 | 2019-07-24 | 2019-08-23 | 2019-07-24 | 2019-08-23 | 106480 | 106480 | 0 | 106480 | 106480 | 1 | FALSE | Normal | TRUE | 2019-07-24 | 2019-08-23 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 23 | 0 |  | Planned | 0% | 920 | 0 | 920 | 920 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.2 | Clean Room Assembly | 0 | 0 | 0 | 0 | 0 | 106480 | PercentComplete | 6% | CP_Phys | Percent Complete |  | Engineering
FALSE |  | A1200 | Install Dish and Telemetry Systems | Titan II Orbiter IMS | 14 | 14 | 2019-08-26 | 2019-09-12 | 0 |  |  | 0 | 2019-08-26 | 2019-09-12 | 2019-08-26 | 2019-09-12 | 55440 | 55440 | 0 | 55440 | 55440 | 1 | FALSE | Normal | TRUE | 2019-08-26 | 2019-09-12 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 14 | 0 |  | Planned | 0% | 336 | 0 | 336 | 336 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.2 | Clean Room Assembly | 0 | 0 | 0 | 0 | 0 | 55440 | PercentComplete | 6% | CP_Phys | Percent Complete |  | Engineering
FALSE |  | A1210 | Install Computer Boards | Titan II Orbiter IMS | 15 | 15 | 2019-09-13 | 2019-10-03 | 0 |  |  | 0 | 2019-09-13 | 2019-10-03 | 2019-09-13 | 2019-10-03 | 8400 | 8400 | 0 | 8400 | 8400 | 1 | FALSE | Normal | TRUE | 2019-09-13 | 2019-10-03 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 0 |  | Planned | 0% | 240 | 0 | 240 | 240 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.2 | Clean Room Assembly | 0 | 0 | 0 | 0 | 0 | 8400 | PercentComplete | 6% | CP_Phys | Percent Complete |  | Engineering
FALSE |  | A1220 | Install Guidance System Electronics | Titan II Orbiter IMS | 34 | 34 | 2019-10-04 | 2019-11-20 | 0 |  |  | 0 | 2019-10-04 | 2019-11-20 | 2019-10-04 | 2019-11-20 | 78120 | 78120 | 0 | 78120 | 78120 | 1 | FALSE | Normal | TRUE | 2019-10-04 | 2019-11-20 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 34 | 0 |  | Planned | 0% | 1360 | 0 | 1360 | 1360 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.2 | Clean Room Assembly | 0 | 0 | 0 | 0 | 0 | 78120 | PercentComplete | 6% | CP_Phys | Percent Complete |  | Engineering
FALSE |  | A1230 | Install Final Exterior Casing Assembly | Titan II Orbiter IMS | 31 | 31 | 2019-11-21 | 2020-01-02 | 0 |  |  | 0 | 2019-11-21 | 2020-01-02 | 2019-11-21 | 2020-01-02 | 19600 | 19600 | 0 | 19600 | 19600 | 1 | FALSE | Normal | TRUE | 2019-11-21 | 2020-01-02 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 31 | 0 |  | Planned | 0% | 496 | 0 | 496 | 496 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.2 | Clean Room Assembly | 0 | 0 | 0 | 0 | 0 | 19600 | PercentComplete | 6% | CP_Phys | Percent Complete |  | Engineering
Merge Hotspot
The total number of activities with a high number of predecessor links.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1140 | Workshop Assembly Complete | Titan II Orbiter IMS | 0 | 0 | 2019-05-02 | 2019-05-02 | 54 |  |  | 54 | 2019-05-02 | 2019-05-02 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Start Milestone | FALSE | 2019-05-02 | 2019-05-02 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.1 | Workshop Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1550 | Instrument Procurement Complete | Titan II Orbiter IMS | 0 | 0 | 2019-07-12 | 2019-07-12 | 2 |  |  | 2 | 2019-07-12 | 2019-07-12 | 2019-07-16 | 2019-07-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-07-12 | 2019-07-12 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1600 | Procurement Complete | Titan II Orbiter IMS | 0 | 0 | 2019-07-16 | 2019-07-16 | 0 |  |  | 0 | 2019-07-16 | 2019-07-16 | 2019-07-16 | 2019-07-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-07-16 | 2019-07-16 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys

## 2020 Details
Fuse® Analyst Report
Workbook: Titan_II_Orbiter Baseline - 62 Activities
Schedule Quality
Created on: 6/2/2017
Created by: Neil
2020: Detailed View | 2020: Detailed View | 2020: Detailed View | 2020: Detailed View
Critical
Number of critical activities
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1230 | Install Final Exterior Casing Assembly | Titan II Orbiter IMS | 31 | 31 | 2019-11-21 | 2020-01-02 | 0 |  |  | 0 | 2019-11-21 | 2020-01-02 | 2019-11-21 | 2020-01-02 | 19600 | 19600 | 0 | 19600 | 19600 | 1 | FALSE | Normal | TRUE | 2019-11-21 | 2020-01-02 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 31 | 0 |  | Planned | 0% | 496 | 0 | 496 | 496 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.2 | Clean Room Assembly | 0 | 0 | 0 | 0 | 0 | 19600 | PercentComplete | 6% | CP_Phys | Percent Complete |  | Engineering
FALSE |  | A1240 | Clean Room Assembly Complete | Titan II Orbiter IMS | 0 | 0 | 2020-01-03 | 2020-01-03 | 0 |  |  | 0 | 2020-01-03 | 2020-01-03 | 2020-01-03 | 2020-01-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Start Milestone | TRUE | 2020-01-03 | 2020-01-03 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.2 | Clean Room Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1260 | Test Start | Titan II Orbiter IMS | 0 | 0 | 2020-01-03 | 2020-01-03 | 0 |  |  | 0 | 2020-01-03 | 2020-01-03 | 2020-01-03 | 2020-01-03 | 0 | 0 | 0 | 0 | 0 | 6 | FALSE | Start Milestone | TRUE | 2020-01-03 | 2020-01-03 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.3 | Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1270 | Hydrazine Testing | Titan II Orbiter IMS | 180 | 180 | 2020-01-03 | 2020-09-10 | 0 |  |  | 0 | 2020-01-03 | 2020-09-10 | 2020-01-03 | 2020-09-10 | 74880 | 74880 | 0 | 74880 | 74880 | 2 | FALSE | Normal | TRUE | 2020-01-03 | 2020-09-10 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 180 | 0 |  | Planned | 0% | 1440 | 0 | 1440 | 1440 | Titan II Orbiter IMS.1.1.2.1.2.3 | Test | 0 | 0 | 0 | 0 | 0 | 74880 | PercentComplete | 6% | CP_Phys | Percent Complete |  | Space Team
FALSE |  | A1340 | Test Complete | Titan II Orbiter IMS | 0 | 0 | 2020-09-11 | 2020-09-11 | 0 |  |  | 0 | 2020-09-11 | 2020-09-11 | 2020-09-11 | 2020-09-11 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Start Milestone | TRUE | 2020-09-11 | 2020-09-11 | FALSE | TRUE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.3 | Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1360 | Launch Preparation Start | Titan II Orbiter IMS | 0 | 0 | 2020-09-11 | 2020-09-11 | 0 |  |  | 0 | 2020-09-11 | 2020-09-11 | 2020-09-11 | 2020-09-11 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Start Milestone | TRUE | 2020-09-11 | 2020-09-11 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.4 | Launch Preparation | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1370 | Drop | Titan II Orbiter IMS | 20 | 20 | 2020-09-11 | 2020-10-08 | 0 |  |  | 0 | 2020-09-11 | 2020-10-08 | 2020-09-11 | 2020-10-08 | 36320 | 36320 | 0 | 36320 | 36320 | 1 | FALSE | Normal | TRUE | 2020-09-11 | 2020-10-08 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 800 | 0 | 800 | 800 | Titan II Orbiter IMS.1.1.2.1.2.4.1.2.4.2 | Stress Tests | 0 | 0 | 0 | 0 | 0 | 36320 | PercentComplete | 6% | CP_Phys | 50/50 | Lincoln | Space Team
FALSE |  | A1380 | G-Force | Titan II Orbiter IMS | 20 | 20 | 2020-10-09 | 2020-11-05 | 0 |  |  | 0 | 2020-10-09 | 2020-11-05 | 2020-10-09 | 2020-11-05 | 30720 | 30720 | 0 | 30720 | 30720 | 1 | FALSE | Normal | TRUE | 2020-10-09 | 2020-11-05 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 640 | 0 | 640 | 640 | Titan II Orbiter IMS.1.1.2.1.2.4.1.2.4.2 | Stress Tests | 0 | 0 | 0 | 0 | 0 | 30720 | PercentComplete | 6% | CP_Phys | 50/50 | Lincoln | Space Team
FALSE |  | A1390 | Vibration | Titan II Orbiter IMS | 39 | 39 | 2020-11-06 | 2020-12-30 | 0 |  |  | 0 | 2020-11-06 | 2020-12-30 | 2020-11-06 | 2020-12-30 | 36320 | 36320 | 0 | 36320 | 36320 | 1 | FALSE | Normal | TRUE | 2020-11-06 | 2020-12-30 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 39 | 0 |  | Planned | 0% | 800 | 0 | 800 | 800 | Titan II Orbiter IMS.1.1.2.1.2.4.1.2.4.2 | Stress Tests | 0 | 0 | 0 | 0 | 0 | 36320 | PercentComplete | 6% | CP_Phys | Percent Complete | Lincoln | Space Team
FALSE |  | A1400 | Final Inspections | Titan II Orbiter IMS | 20 | 20 | 2020-12-31 | 2021-01-27 | 0 |  |  | 0 | 2020-12-31 | 2021-01-27 | 2020-12-31 | 2021-01-27 | 34720 | 34720 | 0 | 34720 | 34720 | 2 | FALSE | Normal | TRUE | 2020-12-31 | 2021-01-27 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 800 | 0 | 800 | 800 | Titan II Orbiter IMS.1.1.2.1.2.4 | Launch Preparation | 0 | 0 | 0 | 0 | 0 | 34720 | PercentComplete | 6% | CP_Phys | 50/50 | Lincoln | Space Team
Insufficient Detail™
Number of activities that have a duration longer than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1270 | Hydrazine Testing | Titan II Orbiter IMS | 180 | 180 | 2020-01-03 | 2020-09-10 | 0 |  |  | 0 | 2020-01-03 | 2020-09-10 | 2020-01-03 | 2020-09-10 | 74880 | 74880 | 0 | 74880 | 74880 | 2 | FALSE | Normal | TRUE | 2020-01-03 | 2020-09-10 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 180 | 0 |  | Planned | 0% | 1440 | 0 | 1440 | 1440 | Titan II Orbiter IMS.1.1.2.1.2.3 | Test | 0 | 0 | 0 | 0 | 0 | 74880 | PercentComplete | 6% | CP_Phys | Percent Complete |  | Space Team
Merge Hotspot
The total number of activities with a high number of predecessor links.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1240 | Clean Room Assembly Complete | Titan II Orbiter IMS | 0 | 0 | 2020-01-03 | 2020-01-03 | 0 |  |  | 0 | 2020-01-03 | 2020-01-03 | 2020-01-03 | 2020-01-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Start Milestone | TRUE | 2020-01-03 | 2020-01-03 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.2 | Clean Room Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1340 | Test Complete | Titan II Orbiter IMS | 0 | 0 | 2020-09-11 | 2020-09-11 | 0 |  |  | 0 | 2020-09-11 | 2020-09-11 | 2020-09-11 | 2020-09-11 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Start Milestone | TRUE | 2020-09-11 | 2020-09-11 | FALSE | TRUE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.3 | Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys

## 2021 Details
Fuse® Analyst Report
Workbook: Titan_II_Orbiter Baseline - 62 Activities
Schedule Quality
Created on: 6/2/2017
Created by: Neil
2021: Detailed View | 2021: Detailed View
Critical
Number of critical activities
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1400 | Final Inspections | Titan II Orbiter IMS | 20 | 20 | 2020-12-31 | 2021-01-27 | 0 |  |  | 0 | 2020-12-31 | 2021-01-27 | 2020-12-31 | 2021-01-27 | 34720 | 34720 | 0 | 34720 | 34720 | 2 | FALSE | Normal | TRUE | 2020-12-31 | 2021-01-27 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 800 | 0 | 800 | 800 | Titan II Orbiter IMS.1.1.2.1.2.4 | Launch Preparation | 0 | 0 | 0 | 0 | 0 | 34720 | PercentComplete | 6% | CP_Phys | 50/50 | Lincoln | Space Team
FALSE |  | A1410 | Clean and Seal for Payload | Titan II Orbiter IMS | 20 | 20 | 2021-01-28 | 2021-02-24 | 0 |  |  | 0 | 2021-01-28 | 2021-02-24 | 2021-01-28 | 2021-02-24 | 19520 | 19520 | 0 | 19520 | 19520 | 1 | FALSE | Normal | TRUE | 2021-01-28 | 2021-02-24 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 480 | 0 | 480 | 480 | Titan II Orbiter IMS.1.1.2.1.2.4 | Launch Preparation | 0 | 0 | 0 | 0 | 0 | 19520 | PercentComplete | 6% | CP_Phys | 50/50 | Lincoln | Space Team
FALSE |  | A1420 | Launch Preparation Complete | Titan II Orbiter IMS | 0 | 0 | 2021-02-25 | 2021-02-25 | 0 |  |  | 0 | 2021-02-25 | 2021-02-25 | 2021-02-25 | 2021-02-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Start Milestone | TRUE | 2021-02-25 | 2021-02-25 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.4 | Launch Preparation | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1440 | Deploy to Launch Facility | Titan II Orbiter IMS | 20 | 20 | 2021-02-25 | 2021-03-24 | 0 |  |  | 0 | 2021-02-25 | 2021-03-24 | 2021-02-25 | 2021-03-24 | 14080 | 14080 | 0 | 14080 | 14080 | 1 | FALSE | Normal | TRUE | 2021-02-25 | 2021-03-24 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 320 | 0 | 320 | 320 | Titan II Orbiter IMS.1.1.2.1.2.5 | Launch | 0 | 0 | 0 | 0 | 0 | 14080 | PercentComplete | 6% | CP_Phys | 50/50 | Lincoln | Space Team
FALSE |  | A1450 | Mount in Atlas V Payload Capsule | Titan II Orbiter IMS | 18 | 18 | 2021-03-25 | 2021-04-19 | 0 |  |  | 0 | 2021-03-25 | 2021-04-19 | 2021-03-25 | 2021-04-19 | 91440 | 91440 | 0 | 91440 | 91440 | 1 | FALSE | Normal | TRUE | 2021-03-25 | 2021-04-19 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 18 | 0 |  | Planned | 0% | 2016 | 0 | 2016 | 2016 | Titan II Orbiter IMS.1.1.2.1.2.5 | Launch | 0 | 0 | 0 | 0 | 0 | 91440 | PercentComplete | 6% | CP_Phys | 50/50 | Lincoln | Space Team
FALSE |  | A1430 | Program Management Complete | Titan II Orbiter IMS | 0 | 0 | 2021-04-20 | 2021-04-20 | 0 |  |  | 0 | 2021-04-20 | 2021-04-20 | 2021-04-19 | 2021-04-19 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | TRUE | 2021-04-20 | 2021-04-20 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.1 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1460 | Atlas V Deployed to Launch Site | Titan II Orbiter IMS | 0 | 0 | 2021-04-20 | 2021-04-20 | 0 |  |  | 0 | 2021-04-20 | 2021-04-20 | 2021-04-19 | 2021-04-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Start Milestone | TRUE | 2021-04-20 | 2021-04-20 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.5 | Launch | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | A1470 | LAUNCH | Titan II Orbiter IMS | 0 | 0 | 2021-04-20 | 2021-04-20 | 0 |  |  | 0 | 2021-04-20 | 2021-04-20 | 2021-04-19 | 2021-04-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Start Milestone | TRUE | 2021-04-20 | 2021-04-20 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.5 | Launch | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys