## Ribbon View
Fuse® Analyst Report
Workbook: TITAN II ORBITER - 379 Activities
DCMA 14 Point
Created on: 9/15/2017
Created by: Neil
DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point | DCMA 14 Point
|  | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line
|  | 2018 | 2018 | 2019 | 2019 | 2020 | 2020 | 2021 | 2021 | 1. Logic | 2. Leads | 3. Lags | 4. SS/FF Relations | 4. SF Relations | 5. Hard Constraint | 6. High Float | 7. Negative Float | 8. High Duration | 9. Invalid Forecast Dates | 9. Invalid Actual Dates | 10. Resources | 11. Missed Activities | 12. Critical Path Test | 13. CPLI | 14. BEI | Score
Ribbons | Titan II Orbiter IMS | [8 empty] | 0 | 0 | 5 | 5 | 0 | 0 | 22 | 0 | 11 | 0 | N/A | 0 | 0 | ✓ | 1 | N/A | 48
Ribbons | Titan II Orbiter IMS | [8 empty] | 0% | 0% | 11% | 11% | 0% | 0% | 51% | 0% | 19% | 0% |  | 0% | 0%
Phase Analyzer | 1. Logic | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Phase Analyzer | 2. Leads | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Phase Analyzer | 3. Lags | 5 | 31% | 0 | 0% | 0 | 0% | 0 | 0%
Phase Analyzer | 4. SS/FF Relations | 4 | 25% | 0 | 0% | 1 | 8% | 0 | 0%
Phase Analyzer | 4. SF Relations | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Phase Analyzer | 5. Hard Constraint | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Phase Analyzer | 6. High Float | 4 | 57% | 11 | 55% | 7 | 58% | 0 | 0%
Phase Analyzer | 7. Negative Float | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Phase Analyzer | 8. High Duration | 0 | 0% | 4 | 17% | 3 | 19% | 0 | 0%
Phase Analyzer | 9. Invalid Forecast Dates | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Phase Analyzer | 9. Invalid Actual Dates | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | 10. Resources | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Phase Analyzer | 11. Missed Activities | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Phase Analyzer | 14. BEI | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | Score | 29 |  | 41 |  | 50 |  | 89

## Ribbon Analysis
Fuse® Analyst Report
Workbook: TITAN II ORBITER - 379 Activities
DCMA 14 Point
Created on: 9/15/2017
Created by: Neil
Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis
Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis
|  | 1. Logic | 2. Leads | 3. Lags | 4. SS/FF Relations | 4. SF Relations | 5. Hard Constraint | 6. High Float | 7. Negative Float | 8. High Duration | 9. Invalid Forecast Dates | 9. Invalid Actual Dates | 10. Resources | 11. Missed Activities | 12. Critical Path Test | 13. CPLI | 14. BEI | Score
Ribbons | Titan II Orbiter IMS | 0 | 0 | 5 | 5 | 0 | 0 | 22 | 0 | 11 | 0 | N/A | 0 | 0 | ✓ | 1 | N/A | 48
Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis
|  | 1. Logic | 2. Leads | 3. Lags | 4. SS/FF Relations | 4. SF Relations | 5. Hard Constraint | 6. High Float | 7. Negative Float | 8. High Duration | 9. Invalid Forecast Dates | 9. Invalid Actual Dates | 10. Resources | 11. Missed Activities | 12. Critical Path Test | 13. CPLI | 14. BEI | Score
Ribbons | Titan II Orbiter IMS | 0% | 0% | 11% | 11% | 0% | 0% | 51% | 0% | 19% | 0% |  | 0% | 0%

## Titan-II-Orbiter-IMS1
Fuse® Analyst Report
Workbook: TITAN II ORBITER - 379 Activities
DCMA 14 Point
Created on: 9/15/2017
Created by: Neil
Titan II Orbiter IMS: Detailed View | Titan II Orbiter IMS: Detailed View | Titan II Orbiter IMS: Detailed View | Titan II Orbiter IMS: Detailed View | Titan II Orbiter IMS: Detailed View
3. Lags
Number of lags in the schedule.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1500 | Electromagnetic Sensor | Titan II Orbiter IMS | 90 | 90 | 2018-10-22 | 2019-02-22 | 102 |  |  | 100 | 2018-10-22 | 2019-02-22 | 2019-03-13 | 2019-07-16 | 170000 | 170000 | 0 | 170000 | 170000 | 1 | FALSE | Normal | FALSE | 2018-10-22 | 2019-02-22 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 170000 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1510 | Ultraviolet Sensor | Titan II Orbiter IMS | 67 | 67 | 2018-11-05 | 2019-02-05 | 115 |  |  | 113 | 2018-11-05 | 2019-02-05 | 2019-04-15 | 2019-07-16 | 140000 | 140000 | 0 | 140000 | 140000 | 1 | FALSE | Normal | FALSE | 2018-11-05 | 2019-02-05 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 67 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 140000 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1520 | Infrared Sensor | Titan II Orbiter IMS | 66 | 66 | 2018-11-19 | 2019-02-18 | 106 |  |  | 104 | 2018-11-19 | 2019-02-18 | 2019-04-16 | 2019-07-16 | 135000 | 135000 | 0 | 135000 | 135000 | 1 | FALSE | Normal | FALSE | 2018-11-19 | 2019-02-18 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 66 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 135000 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1530 | RF Sensor | Titan II Orbiter IMS | 150 | 150 | 2018-12-17 | 2019-07-12 | 2 |  |  | 0 | 2018-12-17 | 2019-07-12 | 2018-12-19 | 2019-07-16 | 2 | 2 | 0 | 1200 | 1200 | 1 | FALSE | Normal | FALSE | 2018-12-17 | 2019-07-12 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 150 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 1200 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1540 | Stereoscopic Camera | Titan II Orbiter IMS | 90 | 90 | 2018-12-31 | 2019-05-03 | 52 |  |  | 50 | 2018-12-31 | 2019-05-03 | 2019-03-13 | 2019-07-16 | 1 | 1 | 0 | 720 | 720 | 1 | FALSE | Normal | FALSE | 2018-12-31 | 2019-05-03 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 720 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
4. SS/FF Relations
Number of Start to Start (SS) and Finish to Finish (FF) logic links. Should be lower than 10%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1000 | Receive Final Concept Design | Titan II Orbiter IMS | 1 | 1 | 2018-10-01 | 2018-10-01 | 0 |  |  | 0 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2144 | 2144 | 0 | 2144 | 2144 | 2 | FALSE | Normal | TRUE | 2018-10-01 | 2018-10-01 |  |  | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Planned | 0% | 48 | 0 | 48 | 48 | Titan II Orbiter IMS.1.1.2.1.2.1.1.2.1.1 | Engineering Design | 0 | 0 | 0 | 0 | 0 | 2144 | PercentComplete | 6% | CP_Phys | 0/100 | Hamilton | Design
FALSE |  | A1010 | Final Design Review | Titan II Orbiter IMS | 5 | 5 | 2018-10-01 | 2018-10-05 | 0 |  |  | 0 | 2018-10-01 | 2018-10-05 | 2018-10-01 | 2018-10-05 | 10720 | 10720 | 0 | 10720 | 10720 | 2 | FALSE | Normal | TRUE | 2018-10-01 | 2018-10-05 |  |  | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 240 | 0 | 240 | 240 | Titan II Orbiter IMS.1.1.2.1.2.1.1.2.1.1 | Engineering Design | 0 | 0 | 0 | 0 | 0 | 10720 | PercentComplete | 6% | CP_Phys | 0/100 | Hamilton | Design
FALSE |  | A1020 | Final Drawings Review | Titan II Orbiter IMS | 5 | 5 | 2018-10-01 | 2018-10-05 | 0 |  |  | 0 | 2018-10-01 | 2018-10-05 | 2018-10-01 | 2018-10-05 | 8320 | 8320 | 0 | 8320 | 8320 | 1 | FALSE | Normal | TRUE | 2018-10-01 | 2018-10-05 |  |  | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 200 | 0 | 200 | 200 | Titan II Orbiter IMS.1.1.2.1.2.1.1.2.1.1 | Engineering Design | 0 | 0 | 0 | 0 | 0 | 8320 | PercentComplete | 6% | CP_Phys | 0/100 | Hamilton | Design
FALSE |  | A1050 | Jig Assembly | Titan II Orbiter IMS | 40 | 40 | 2018-10-08 | 2018-11-30 | 69 |  |  | 0 | 2018-10-08 | 2018-11-30 | 2019-01-11 | 2019-03-07 | 88320 | 88320 | 0 | 88320 | 88320 | 3 | FALSE | Normal | FALSE | 2018-10-08 | 2018-11-30 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 0 |  | Planned | 0% | 1920 | 0 | 1920 | 1920 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.1 | Workshop Assembly | 0 | 0 | 0 | 0 | 0 | 88320 | PercentComplete | 6% | CP_Phys | Percent Complete | Jackson | Engineering
FALSE |  | A1330 | Sustained Vacuum High Voltage Ionization Testing | Titan II Orbiter IMS | 60 | 60 | 2020-01-03 | 2020-03-26 | 120 |  |  | 120 | 2020-01-03 | 2020-03-26 | 2020-06-19 | 2020-09-10 | 15360 | 15360 | 0 | 15360 | 15360 | 1 | FALSE | Normal | FALSE | 2020-01-03 | 2020-03-26 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 0 |  | Planned | 0% | 288 | 0 | 288 | 288 | Titan II Orbiter IMS.1.1.2.1.2.3 | Test | 0 | 0 | 0 | 0 | 0 | 15360 | PercentComplete | 6% | CP_Phys | 50/50 |  | Space Team
6. High Float
Number of activities with total float greater than 2 months. Should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1050 | Jig Assembly | Titan II Orbiter IMS | 40 | 40 | 2018-10-08 | 2018-11-30 | 69 |  |  | 0 | 2018-10-08 | 2018-11-30 | 2019-01-11 | 2019-03-07 | 88320 | 88320 | 0 | 88320 | 88320 | 3 | FALSE | Normal | FALSE | 2018-10-08 | 2018-11-30 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 0 |  | Planned | 0% | 1920 | 0 | 1920 | 1920 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.1 | Workshop Assembly | 0 | 0 | 0 | 0 | 0 | 88320 | PercentComplete | 6% | CP_Phys | Percent Complete | Jackson | Engineering
FALSE |  | A1090 | Installation of Guidance Controls | Titan II Orbiter IMS | 30 | 30 | 2018-10-08 | 2018-11-16 | 54 |  |  | 0 | 2018-10-08 | 2018-11-16 | 2018-12-21 | 2019-01-31 | 152100 | 152100 | 0 | 152100 | 152100 | 1 | FALSE | Normal | FALSE | 2018-10-08 | 2018-11-16 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 3 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 2040.01 | 0 | 3060 | 3060 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.1.1.2.2.1.6 | Guidance Controls | 0 | 0 | 0 | 0 | 0 | 152100 | PercentComplete | 6% | CP_Phys | Percent Complete | Jackson | Engineering
FALSE |  | A1500 | Electromagnetic Sensor | Titan II Orbiter IMS | 90 | 90 | 2018-10-22 | 2019-02-22 | 102 |  |  | 100 | 2018-10-22 | 2019-02-22 | 2019-03-13 | 2019-07-16 | 170000 | 170000 | 0 | 170000 | 170000 | 1 | FALSE | Normal | FALSE | 2018-10-22 | 2019-02-22 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 170000 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1510 | Ultraviolet Sensor | Titan II Orbiter IMS | 67 | 67 | 2018-11-05 | 2019-02-05 | 115 |  |  | 113 | 2018-11-05 | 2019-02-05 | 2019-04-15 | 2019-07-16 | 140000 | 140000 | 0 | 140000 | 140000 | 1 | FALSE | Normal | FALSE | 2018-11-05 | 2019-02-05 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 67 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 140000 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1100 | Wiring Completed | Titan II Orbiter IMS | 23 | 23 | 2018-11-19 | 2018-12-19 | 54 |  |  | 0 | 2018-11-19 | 2018-12-19 | 2019-02-01 | 2019-03-05 | 29200 | 29200 | 0 | 29200 | 29200 | 1 | FALSE | Normal | FALSE | 2018-11-19 | 2018-12-19 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 23 | 0 |  | Planned | 0% | 504 | 0 | 720 | 720 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.1.1.2.2.1.6 | Guidance Controls | 0 | 0 | 0 | 0 | 0 | 29200 | PercentComplete | 6% | CP_Phys | Percent Complete | Jackson | Engineering
FALSE |  | A1520 | Infrared Sensor | Titan II Orbiter IMS | 66 | 66 | 2018-11-19 | 2019-02-18 | 106 |  |  | 104 | 2018-11-19 | 2019-02-18 | 2019-04-16 | 2019-07-16 | 135000 | 135000 | 0 | 135000 | 135000 | 1 | FALSE | Normal | FALSE | 2018-11-19 | 2019-02-18 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 66 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 135000 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1060 | Wiring Harness Installation | Titan II Orbiter IMS | 15 | 15 | 2018-12-03 | 2018-12-21 | 69 |  |  | 0 | 2018-12-03 | 2018-12-21 | 2019-03-08 | 2019-03-28 | 27600 | 27600 | 0 | 27600 | 27600 | 2 | FALSE | Normal | FALSE | 2018-12-03 | 2018-12-21 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 0 |  | Planned | 0% | 720 | 0 | 720 | 720 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.1 | Workshop Assembly | 0 | 0 | 0 | 0 | 0 | 27600 | PercentComplete | 6% | CP_Phys | 0/100 | Jackson | Engineering
FALSE |  | A1110 | Software Installed | Titan II Orbiter IMS | 31 | 31 | 2018-12-20 | 2019-01-31 | 54 |  |  | 0 | 2018-12-20 | 2019-01-31 | 2019-03-06 | 2019-04-17 | 17360 | 17360 | 0 | 17360 | 17360 | 1 | FALSE | Normal | FALSE | 2018-12-20 | 2019-01-31 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 31 | 0 |  | Planned | 0% | 496 | 0 | 496 | 496 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.1.1.2.2.1.6 | Guidance Controls | 0 | 0 | 0 | 0 | 0 | 17360 | PercentComplete | 6% | CP_Phys | Percent Complete | Jackson | Engineering
FALSE |  | A1070 | Power Supply | Titan II Orbiter IMS | 35 | 35 | 2018-12-24 | 2019-02-08 | 69 |  |  | 0 | 2018-12-24 | 2019-02-08 | 2019-03-29 | 2019-05-16 | 90000 | 90000 | 0 | 90000 | 90000 | 2 | FALSE | Normal | FALSE | 2018-12-24 | 2019-02-08 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 0 |  | Planned | 0% | 1680 | 0 | 1680 | 1680 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.1 | Workshop Assembly | 0 | 0 | 0 | 0 | 0 | 90000 | PercentComplete | 6% | CP_Phys | 50/50 | Jackson | Engineering
FALSE |  | A1540 | Stereoscopic Camera | Titan II Orbiter IMS | 90 | 90 | 2018-12-31 | 2019-05-03 | 52 |  |  | 50 | 2018-12-31 | 2019-05-03 | 2019-03-13 | 2019-07-16 | 1 | 1 | 0 | 720 | 720 | 1 | FALSE | Normal | FALSE | 2018-12-31 | 2019-05-03 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 720 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1120 | Tested | Titan II Orbiter IMS | 29 | 29 | 2019-02-01 | 2019-03-13 | 54 |  |  | 0 | 2019-02-01 | 2019-03-13 | 2019-04-18 | 2019-05-28 | 40368 | 40368 | 0 | 40368 | 40368 | 2 | FALSE | Normal | FALSE | 2019-02-01 | 2019-03-13 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 29 | 0 |  | Planned | 0% | 928 | 0 | 928 | 928 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.1.1.2.2.1.6 | Guidance Controls | 0 | 0 | 0 | 0 | 0 | 40368 | PercentComplete | 6% | CP_Phys | Percent Complete | Jackson | Engineering
FALSE |  | A1080 | Solar Deployment Assembly | Titan II Orbiter IMS | 43 | 43 | 2019-02-11 | 2019-04-10 | 69 |  |  | 15 | 2019-02-11 | 2019-04-10 | 2019-05-17 | 2019-07-16 | 70720 | 70720 | 0 | 70720 | 70720 | 1 | FALSE | Normal | FALSE | 2019-02-11 | 2019-04-10 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 43 | 0 |  | Planned | 0% | 1032 | 0 | 1032 | 1032 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.1 | Workshop Assembly | 0 | 0 | 0 | 0 | 0 | 70720 | PercentComplete | 6% | CP_Phys | Percent Complete | Jackson | Engineering
FALSE |  | A1130 | Sign off | Titan II Orbiter IMS | 35 | 35 | 2019-03-14 | 2019-05-01 | 54 |  |  | 0 | 2019-03-14 | 2019-05-01 | 2019-05-29 | 2019-07-16 | 27206.67 | 27206.67 | 0 | 27206.6667 | 27206.6667 | 1 | FALSE | Normal | FALSE | 2019-03-14 | 2019-05-01 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 3 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 0 |  | Planned | 0% | 513.3333 | 0 | 513.3333 | 513.3333 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.1.1.2.2.1.6 | Guidance Controls | 0 | 0 | 0 | 0 | 0 | 27206.67 | PercentComplete | 6% | CP_Phys | Percent Complete | Jackson | Engineering
FALSE |  | A1170 | Install Sensor Instruments | Titan II Orbiter IMS | 3 | 3 | 2019-07-24 | 2019-07-26 | 114 |  |  | 114 | 2019-07-24 | 2019-07-26 | 2019-12-31 | 2020-01-02 | 107189 | 107189 | 0 | 107189 | 107189 | 1 | FALSE | Normal | FALSE | 2019-07-24 | 2019-07-26 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 0 |  | Planned | 0% | 96 | 0 | 96 | 96 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.2 | Clean Room Assembly | 0 | 0 | 0 | 0 | 0 | 107189 | PercentComplete | 6% | CP_Phys | Percent Complete |  | Engineering
FALSE |  | A1180 | Install Stereoscopic Cameras | Titan II Orbiter IMS | 9 | 9 | 2019-07-24 | 2019-08-05 | 108 |  |  | 108 | 2019-07-24 | 2019-08-05 | 2019-12-23 | 2020-01-02 | 65392 | 65392 | 0 | 65392 | 65392 | 1 | FALSE | Normal | FALSE | 2019-07-24 | 2019-08-05 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 9 | 0 |  | Planned | 0% | 216 | 0 | 216 | 216 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.2 | Clean Room Assembly | 0 | 0 | 0 | 0 | 0 | 65392 | PercentComplete | 6% | CP_Phys | Percent Complete |  | Engineering
FALSE |  | A1330 | Sustained Vacuum High Voltage Ionization Testing | Titan II Orbiter IMS | 60 | 60 | 2020-01-03 | 2020-03-26 | 120 |  |  | 120 | 2020-01-03 | 2020-03-26 | 2020-06-19 | 2020-09-10 | 15360 | 15360 | 0 | 15360 | 15360 | 1 | FALSE | Normal | FALSE | 2020-01-03 | 2020-03-26 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 0 |  | Planned | 0% | 288 | 0 | 288 | 288 | Titan II Orbiter IMS.1.1.2.1.2.3 | Test | 0 | 0 | 0 | 0 | 0 | 15360 | PercentComplete | 6% | CP_Phys | 50/50 |  | Space Team
FALSE |  | A1280 | Test Nitrogen Sensor | Titan II Orbiter IMS | 30 | 30 | 2020-01-03 | 2020-02-13 | 150 |  |  | 150 | 2020-01-03 | 2020-02-13 | 2020-07-31 | 2020-09-10 | 37440 | 37440 | 0 | 37440 | 37440 | 1 | FALSE | Normal | FALSE | 2020-01-03 | 2020-02-13 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 24 | 0 | 960 | 960 | Titan II Orbiter IMS.1.1.2.1.2.3.1.2.3.3 | Instrument Characterization | 0 | 0 | 0 | 0 | 0 | 37440 | PercentComplete | 6% | CP_Phys | Level of Effort |  | Space Team
FALSE |  | A1290 | Test Oxigen Sensor | Titan II Orbiter IMS | 30 | 30 | 2020-01-03 | 2020-02-13 | 150 |  |  | 150 | 2020-01-03 | 2020-02-13 | 2020-07-31 | 2020-09-10 | 37440 | 37440 | 0 | 37440 | 37440 | 1 | FALSE | Normal | FALSE | 2020-01-03 | 2020-02-13 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 24 | 0 | 960 | 960 | Titan II Orbiter IMS.1.1.2.1.2.3.1.2.3.3 | Instrument Characterization | 0 | 0 | 0 | 0 | 0 | 37440 | PercentComplete | 6% | CP_Phys | Level of Effort |  | Space Team
FALSE |  | A1300 | Test Hydrogen Sensor | Titan II Orbiter IMS | 30 | 30 | 2020-01-03 | 2020-02-13 | 150 |  |  | 150 | 2020-01-03 | 2020-02-13 | 2020-07-31 | 2020-09-10 | 37440 | 37440 | 0 | 37440 | 37440 | 1 | FALSE | Normal | FALSE | 2020-01-03 | 2020-02-13 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 24 | 0 | 960 | 960 | Titan II Orbiter IMS.1.1.2.1.2.3.1.2.3.3 | Instrument Characterization | 0 | 0 | 0 | 0 | 0 | 37440 | PercentComplete | 6% | CP_Phys | Level of Effort |  | Space Team
FALSE |  | A1310 | Test Helium Sensor | Titan II Orbiter IMS | 30 | 30 | 2020-01-03 | 2020-02-13 | 150 |  |  | 150 | 2020-01-03 | 2020-02-13 | 2020-07-31 | 2020-09-10 | 37440 | 37440 | 0 | 37440 | 37440 | 1 | FALSE | Normal | FALSE | 2020-01-03 | 2020-02-13 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 24 | 0 | 960 | 960 | Titan II Orbiter IMS.1.1.2.1.2.3.1.2.3.3 | Instrument Characterization | 0 | 0 | 0 | 0 | 0 | 37440 | PercentComplete | 6% | CP_Phys | Level of Effort |  | Space Team
FALSE |  | A1320 | Test Methane Sensor | Titan II Orbiter IMS | 30 | 30 | 2020-01-03 | 2020-02-13 | 150 |  |  | 150 | 2020-01-03 | 2020-02-13 | 2020-07-31 | 2020-09-10 | 37440 | 37440 | 0 | 37440 | 37440 | 1 | FALSE | Normal | FALSE | 2020-01-03 | 2020-02-13 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 24 | 0 | 960 | 960 | Titan II Orbiter IMS.1.1.2.1.2.3.1.2.3.3 | Instrument Characterization | 0 | 0 | 0 | 0 | 0 | 37440 | PercentComplete | 6% | CP_Phys | Level of Effort |  | Space Team
FALSE |  | A1590 | Solar Panels and Systems Parts | Titan II Orbiter IMS | 71 | 71 | 2020-09-11 | 2020-12-18 | 86 |  |  | 86 | 2020-09-11 | 2020-12-18 | 2021-01-11 | 2021-04-19 | 43744 | 43744 | 0 | 43744 | 43744 | 1 | FALSE | Normal | FALSE | 2020-09-11 | 2020-12-18 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 71 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 43744 | PercentComplete | 6% | CP_Phys | Planning Package | Lincoln | Procurement
8. High Duration
Total number of activities that have a duration longer than 2 months. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1350 | Program Management | Titan II Orbiter IMS | 666 | 666 | 2018-10-01 | 2021-04-19 | 0 |  |  | 0 | 2018-10-01 | 2021-04-19 | 2021-04-19 | 2021-04-19 | 903104 | 903104 | 0 | 0 | 0 | 0 | FALSE | Level of Effort | TRUE | 2018-10-01 | 2021-04-19 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3 | 7 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | LevelOfEffort | 666 | 0 |  | Planned | 0% | 18115.2 | 0 | 31968 | 31968 | Titan II Orbiter IMS.1.1.1 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Level of Effort | Jefferson | Mangement
FALSE |  | A1490 | Procurement | Titan II Orbiter IMS | 202 | 202 | 2018-10-08 | 2019-07-16 | 0 |  |  | 0 | 2018-10-08 | 2019-07-16 | 2019-07-16 | 2019-07-16 | 48640 | 48640 | 0 | 48640 | 48640 | 1 | FALSE | Level of Effort | TRUE | 2018-10-08 | 2019-07-16 |  |  | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | LevelOfEffort | 202 | 0 |  | Planned | 0% | 1616 | 0 | 1616 | 1616 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 48640 | PercentComplete | 6% | CP_Phys | Level of Effort | Jefferson | Mangement
FALSE |  | A1560 | Acquire Laptop Computers | Titan II Orbiter IMS | 90 | 90 | 2018-10-08 | 2019-02-08 | 0 |  |  | 0 | 2018-10-08 | 2019-02-08 | 2018-10-08 | 2019-02-08 | 216999.98 | 216999.98 | 0 | 216999.98 | 216999.98 | 1 | FALSE | Normal | TRUE | 2018-10-08 | 2019-02-08 |  |  | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 216999.98 | PercentComplete | 6% | CP_Phys | Units Complete | Lincoln | Procurement
FALSE |  | A1500 | Electromagnetic Sensor | Titan II Orbiter IMS | 90 | 90 | 2018-10-22 | 2019-02-22 | 102 |  |  | 100 | 2018-10-22 | 2019-02-22 | 2019-03-13 | 2019-07-16 | 170000 | 170000 | 0 | 170000 | 170000 | 1 | FALSE | Normal | FALSE | 2018-10-22 | 2019-02-22 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 170000 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1510 | Ultraviolet Sensor | Titan II Orbiter IMS | 67 | 67 | 2018-11-05 | 2019-02-05 | 115 |  |  | 113 | 2018-11-05 | 2019-02-05 | 2019-04-15 | 2019-07-16 | 140000 | 140000 | 0 | 140000 | 140000 | 1 | FALSE | Normal | FALSE | 2018-11-05 | 2019-02-05 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 67 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 140000 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1520 | Infrared Sensor | Titan II Orbiter IMS | 66 | 66 | 2018-11-19 | 2019-02-18 | 106 |  |  | 104 | 2018-11-19 | 2019-02-18 | 2019-04-16 | 2019-07-16 | 135000 | 135000 | 0 | 135000 | 135000 | 1 | FALSE | Normal | FALSE | 2018-11-19 | 2019-02-18 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 66 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 135000 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1530 | RF Sensor | Titan II Orbiter IMS | 150 | 150 | 2018-12-17 | 2019-07-12 | 2 |  |  | 0 | 2018-12-17 | 2019-07-12 | 2018-12-19 | 2019-07-16 | 2 | 2 | 0 | 1200 | 1200 | 1 | FALSE | Normal | FALSE | 2018-12-17 | 2019-07-12 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 150 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 1200 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1540 | Stereoscopic Camera | Titan II Orbiter IMS | 90 | 90 | 2018-12-31 | 2019-05-03 | 52 |  |  | 50 | 2018-12-31 | 2019-05-03 | 2019-03-13 | 2019-07-16 | 1 | 1 | 0 | 720 | 720 | 1 | FALSE | Normal | FALSE | 2018-12-31 | 2019-05-03 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 720 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1570 | Acquire Cabling | Titan II Orbiter IMS | 67 | 67 | 2019-02-11 | 2019-05-14 | 0 |  |  | 0 | 2019-02-11 | 2019-05-14 | 2019-02-11 | 2019-05-14 | 3000 | 3000 | 0 | 2999.9997 | 2999.9997 | 1 | FALSE | Normal | TRUE | 2019-02-11 | 2019-05-14 |  |  | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 67 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 3000 | PercentComplete | 6% | CP_Phys | Units Complete | Lincoln | Procurement
FALSE |  | A1580 | Assemble and Install Software | Titan II Orbiter IMS | 45 | 45 | 2019-05-15 | 2019-07-16 | 0 |  |  | 0 | 2019-05-15 | 2019-07-16 | 2019-05-15 | 2019-07-16 | 63000 | 63000 | 0 | 63000 | 63000 | 1 | FALSE | Normal | TRUE | 2019-05-15 | 2019-07-16 |  |  | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 45 | 0 |  | Planned | 0% | 1800 | 0 | 1800 | 1800 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 63000 | PercentComplete | 6% | CP_Phys | Units Complete | Lincoln | Procurement
FALSE |  | A1270 | Hydrazine Testing | Titan II Orbiter IMS | 180 | 180 | 2020-01-03 | 2020-09-10 | 0 |  |  | 0 | 2020-01-03 | 2020-09-10 | 2020-01-03 | 2020-09-10 | 74880 | 74880 | 0 | 74880 | 74880 | 2 | FALSE | Normal | TRUE | 2020-01-03 | 2020-09-10 |  |  | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 180 | 0 |  | Planned | 0% | 1440 | 0 | 1440 | 1440 | Titan II Orbiter IMS.1.1.2.1.2.3 | Test | 0 | 0 | 0 | 0 | 0 | 74880 | PercentComplete | 6% | CP_Phys | Percent Complete |  | Space Team
FALSE |  | A1330 | Sustained Vacuum High Voltage Ionization Testing | Titan II Orbiter IMS | 60 | 60 | 2020-01-03 | 2020-03-26 | 120 |  |  | 120 | 2020-01-03 | 2020-03-26 | 2020-06-19 | 2020-09-10 | 15360 | 15360 | 0 | 15360 | 15360 | 1 | FALSE | Normal | FALSE | 2020-01-03 | 2020-03-26 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 0 |  | Planned | 0% | 288 | 0 | 288 | 288 | Titan II Orbiter IMS.1.1.2.1.2.3 | Test | 0 | 0 | 0 | 0 | 0 | 15360 | PercentComplete | 6% | CP_Phys | 50/50 |  | Space Team
FALSE |  | A1590 | Solar Panels and Systems Parts | Titan II Orbiter IMS | 71 | 71 | 2020-09-11 | 2020-12-18 | 86 |  |  | 86 | 2020-09-11 | 2020-12-18 | 2021-01-11 | 2021-04-19 | 43744 | 43744 | 0 | 43744 | 43744 | 1 | FALSE | Normal | FALSE | 2020-09-11 | 2020-12-18 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 71 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 43744 | PercentComplete | 6% | CP_Phys | Planning Package | Lincoln | Procurement

## Phase Analysis
Fuse® Analyst Report
Workbook: TITAN II ORBITER - 379 Activities
DCMA 14 Point
Created on: 9/15/2017
Created by: Neil
Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis
Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis
|  | Time Line | Time Line | Time Line | Time Line
|  | 2018 | 2019 | 2020 | 2021
Phase Analyzer | 1. Logic | 0 | 0 | 0 | 0
Phase Analyzer | 2. Leads | 0 | 0 | 0 | 0
Phase Analyzer | 3. Lags | 5 | 0 | 0 | 0
Phase Analyzer | 4. SS/FF Relations | 4 | 0 | 1 | 0
Phase Analyzer | 4. SF Relations | 0 | 0 | 0 | 0
Phase Analyzer | 5. Hard Constraint | 0 | 0 | 0 | 0
Phase Analyzer | 6. High Float | 4 | 11 | 7 | 0
Phase Analyzer | 7. Negative Float | 0 | 0 | 0 | 0
Phase Analyzer | 8. High Duration | 0 | 4 | 3 | 0
Phase Analyzer | 9. Invalid Forecast Dates | 0 | 0 | 0 | 0
Phase Analyzer | 9. Invalid Actual Dates | N/A | N/A | N/A | N/A
Phase Analyzer | 10. Resources | 0 | 0 | 0 | 0
Phase Analyzer | 11. Missed Activities | 0 | 0 | 0 | 0
Phase Analyzer | 14. BEI | N/A | N/A | N/A | N/A
Phase Analyzer | Score | 29 | 41 | 50 | 89
Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis
|  | Time Line | Time Line | Time Line | Time Line
|  | 2018 | 2019 | 2020 | 2021
Phase Analyzer | 1. Logic | 0% | 0% | 0% | 0%
Phase Analyzer | 2. Leads | 0% | 0% | 0% | 0%
Phase Analyzer | 3. Lags | 31% | 0% | 0% | 0%
Phase Analyzer | 4. SS/FF Relations | 25% | 0% | 8% | 0%
Phase Analyzer | 4. SF Relations | 0% | 0% | 0% | 0%
Phase Analyzer | 5. Hard Constraint | 0% | 0% | 0% | 0%
Phase Analyzer | 6. High Float | 57% | 55% | 58% | 0%
Phase Analyzer | 7. Negative Float | 0% | 0% | 0% | 0%
Phase Analyzer | 8. High Duration | 0% | 17% | 19% | 0%
Phase Analyzer | 9. Invalid Forecast Dates | 0% | 0% | 0% | 0%
Phase Analyzer | 9. Invalid Actual Dates
Phase Analyzer | 10. Resources | 0% | 0% | 0% | 0%
Phase Analyzer | 11. Missed Activities | 0% | 0% | 0% | 0%
Phase Analyzer | 14. BEI
Phase Analyzer | Score

## 2018 Details
Fuse® Analyst Report
Workbook: TITAN II ORBITER - 379 Activities
DCMA 14 Point
Created on: 9/15/2017
Created by: Neil
2018: Detailed View | 2018: Detailed View | 2018: Detailed View | 2018: Detailed View | 2018: Detailed View
3. Lags
Number of lags in the schedule.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1500 | Electromagnetic Sensor | Titan II Orbiter IMS | 90 | 90 | 2018-10-22 | 2019-02-22 | 102 |  |  | 100 | 2018-10-22 | 2019-02-22 | 2019-03-13 | 2019-07-16 | 170000 | 170000 | 0 | 170000 | 170000 | 1 | FALSE | Normal | FALSE | 2018-10-22 | 2019-02-22 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 170000 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1510 | Ultraviolet Sensor | Titan II Orbiter IMS | 67 | 67 | 2018-11-05 | 2019-02-05 | 115 |  |  | 113 | 2018-11-05 | 2019-02-05 | 2019-04-15 | 2019-07-16 | 140000 | 140000 | 0 | 140000 | 140000 | 1 | FALSE | Normal | FALSE | 2018-11-05 | 2019-02-05 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 67 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 140000 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1520 | Infrared Sensor | Titan II Orbiter IMS | 66 | 66 | 2018-11-19 | 2019-02-18 | 106 |  |  | 104 | 2018-11-19 | 2019-02-18 | 2019-04-16 | 2019-07-16 | 135000 | 135000 | 0 | 135000 | 135000 | 1 | FALSE | Normal | FALSE | 2018-11-19 | 2019-02-18 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 66 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 135000 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1530 | RF Sensor | Titan II Orbiter IMS | 150 | 150 | 2018-12-17 | 2019-07-12 | 2 |  |  | 0 | 2018-12-17 | 2019-07-12 | 2018-12-19 | 2019-07-16 | 2 | 2 | 0 | 1200 | 1200 | 1 | FALSE | Normal | FALSE | 2018-12-17 | 2019-07-12 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 150 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 1200 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1540 | Stereoscopic Camera | Titan II Orbiter IMS | 90 | 90 | 2018-12-31 | 2019-05-03 | 52 |  |  | 50 | 2018-12-31 | 2019-05-03 | 2019-03-13 | 2019-07-16 | 1 | 1 | 0 | 720 | 720 | 1 | FALSE | Normal | FALSE | 2018-12-31 | 2019-05-03 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 720 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
4. SS/FF Relations
Number of Start to Start (SS) and Finish to Finish (FF) logic links. Should be lower than 10%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1000 | Receive Final Concept Design | Titan II Orbiter IMS | 1 | 1 | 2018-10-01 | 2018-10-01 | 0 |  |  | 0 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2144 | 2144 | 0 | 2144 | 2144 | 2 | FALSE | Normal | TRUE | 2018-10-01 | 2018-10-01 |  |  | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Planned | 0% | 48 | 0 | 48 | 48 | Titan II Orbiter IMS.1.1.2.1.2.1.1.2.1.1 | Engineering Design | 0 | 0 | 0 | 0 | 0 | 2144 | PercentComplete | 6% | CP_Phys | 0/100 | Hamilton | Design
FALSE |  | A1010 | Final Design Review | Titan II Orbiter IMS | 5 | 5 | 2018-10-01 | 2018-10-05 | 0 |  |  | 0 | 2018-10-01 | 2018-10-05 | 2018-10-01 | 2018-10-05 | 10720 | 10720 | 0 | 10720 | 10720 | 2 | FALSE | Normal | TRUE | 2018-10-01 | 2018-10-05 |  |  | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 240 | 0 | 240 | 240 | Titan II Orbiter IMS.1.1.2.1.2.1.1.2.1.1 | Engineering Design | 0 | 0 | 0 | 0 | 0 | 10720 | PercentComplete | 6% | CP_Phys | 0/100 | Hamilton | Design
FALSE |  | A1020 | Final Drawings Review | Titan II Orbiter IMS | 5 | 5 | 2018-10-01 | 2018-10-05 | 0 |  |  | 0 | 2018-10-01 | 2018-10-05 | 2018-10-01 | 2018-10-05 | 8320 | 8320 | 0 | 8320 | 8320 | 1 | FALSE | Normal | TRUE | 2018-10-01 | 2018-10-05 |  |  | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 200 | 0 | 200 | 200 | Titan II Orbiter IMS.1.1.2.1.2.1.1.2.1.1 | Engineering Design | 0 | 0 | 0 | 0 | 0 | 8320 | PercentComplete | 6% | CP_Phys | 0/100 | Hamilton | Design
FALSE |  | A1050 | Jig Assembly | Titan II Orbiter IMS | 40 | 40 | 2018-10-08 | 2018-11-30 | 69 |  |  | 0 | 2018-10-08 | 2018-11-30 | 2019-01-11 | 2019-03-07 | 88320 | 88320 | 0 | 88320 | 88320 | 3 | FALSE | Normal | FALSE | 2018-10-08 | 2018-11-30 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 0 |  | Planned | 0% | 1920 | 0 | 1920 | 1920 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.1 | Workshop Assembly | 0 | 0 | 0 | 0 | 0 | 88320 | PercentComplete | 6% | CP_Phys | Percent Complete | Jackson | Engineering
6. High Float
Number of activities with total float greater than 2 months. Should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1050 | Jig Assembly | Titan II Orbiter IMS | 40 | 40 | 2018-10-08 | 2018-11-30 | 69 |  |  | 0 | 2018-10-08 | 2018-11-30 | 2019-01-11 | 2019-03-07 | 88320 | 88320 | 0 | 88320 | 88320 | 3 | FALSE | Normal | FALSE | 2018-10-08 | 2018-11-30 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 0 |  | Planned | 0% | 1920 | 0 | 1920 | 1920 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.1 | Workshop Assembly | 0 | 0 | 0 | 0 | 0 | 88320 | PercentComplete | 6% | CP_Phys | Percent Complete | Jackson | Engineering
FALSE |  | A1090 | Installation of Guidance Controls | Titan II Orbiter IMS | 30 | 30 | 2018-10-08 | 2018-11-16 | 54 |  |  | 0 | 2018-10-08 | 2018-11-16 | 2018-12-21 | 2019-01-31 | 152100 | 152100 | 0 | 152100 | 152100 | 1 | FALSE | Normal | FALSE | 2018-10-08 | 2018-11-16 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 3 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 2040.01 | 0 | 3060 | 3060 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.1.1.2.2.1.6 | Guidance Controls | 0 | 0 | 0 | 0 | 0 | 152100 | PercentComplete | 6% | CP_Phys | Percent Complete | Jackson | Engineering
FALSE |  | A1100 | Wiring Completed | Titan II Orbiter IMS | 23 | 23 | 2018-11-19 | 2018-12-19 | 54 |  |  | 0 | 2018-11-19 | 2018-12-19 | 2019-02-01 | 2019-03-05 | 29200 | 29200 | 0 | 29200 | 29200 | 1 | FALSE | Normal | FALSE | 2018-11-19 | 2018-12-19 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 23 | 0 |  | Planned | 0% | 504 | 0 | 720 | 720 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.1.1.2.2.1.6 | Guidance Controls | 0 | 0 | 0 | 0 | 0 | 29200 | PercentComplete | 6% | CP_Phys | Percent Complete | Jackson | Engineering
FALSE |  | A1060 | Wiring Harness Installation | Titan II Orbiter IMS | 15 | 15 | 2018-12-03 | 2018-12-21 | 69 |  |  | 0 | 2018-12-03 | 2018-12-21 | 2019-03-08 | 2019-03-28 | 27600 | 27600 | 0 | 27600 | 27600 | 2 | FALSE | Normal | FALSE | 2018-12-03 | 2018-12-21 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 0 |  | Planned | 0% | 720 | 0 | 720 | 720 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.1 | Workshop Assembly | 0 | 0 | 0 | 0 | 0 | 27600 | PercentComplete | 6% | CP_Phys | 0/100 | Jackson | Engineering
8. High Duration
Total number of activities that have a duration longer than 2 months. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1350 | Program Management | Titan II Orbiter IMS | 666 | 666 | 2018-10-01 | 2021-04-19 | 0 |  |  | 0 | 2018-10-01 | 2021-04-19 | 2021-04-19 | 2021-04-19 | 903104 | 903104 | 0 | 0 | 0 | 0 | FALSE | Level of Effort | TRUE | 2018-10-01 | 2021-04-19 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3 | 7 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | LevelOfEffort | 666 | 0 |  | Planned | 0% | 18115.2 | 0 | 31968 | 31968 | Titan II Orbiter IMS.1.1.1 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Level of Effort | Jefferson | Mangement
FALSE |  | A1490 | Procurement | Titan II Orbiter IMS | 202 | 202 | 2018-10-08 | 2019-07-16 | 0 |  |  | 0 | 2018-10-08 | 2019-07-16 | 2019-07-16 | 2019-07-16 | 48640 | 48640 | 0 | 48640 | 48640 | 1 | FALSE | Level of Effort | TRUE | 2018-10-08 | 2019-07-16 |  |  | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | LevelOfEffort | 202 | 0 |  | Planned | 0% | 1616 | 0 | 1616 | 1616 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 48640 | PercentComplete | 6% | CP_Phys | Level of Effort | Jefferson | Mangement
FALSE |  | A1560 | Acquire Laptop Computers | Titan II Orbiter IMS | 90 | 90 | 2018-10-08 | 2019-02-08 | 0 |  |  | 0 | 2018-10-08 | 2019-02-08 | 2018-10-08 | 2019-02-08 | 216999.98 | 216999.98 | 0 | 216999.98 | 216999.98 | 1 | FALSE | Normal | TRUE | 2018-10-08 | 2019-02-08 |  |  | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 216999.98 | PercentComplete | 6% | CP_Phys | Units Complete | Lincoln | Procurement
FALSE |  | A1500 | Electromagnetic Sensor | Titan II Orbiter IMS | 90 | 90 | 2018-10-22 | 2019-02-22 | 102 |  |  | 100 | 2018-10-22 | 2019-02-22 | 2019-03-13 | 2019-07-16 | 170000 | 170000 | 0 | 170000 | 170000 | 1 | FALSE | Normal | FALSE | 2018-10-22 | 2019-02-22 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 170000 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement

## 2019 Details
Fuse® Analyst Report
Workbook: TITAN II ORBITER - 379 Activities
DCMA 14 Point
Created on: 9/15/2017
Created by: Neil
2019: Detailed View | 2019: Detailed View | 2019: Detailed View
6. High Float
Number of activities with total float greater than 2 months. Should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1500 | Electromagnetic Sensor | Titan II Orbiter IMS | 90 | 90 | 2018-10-22 | 2019-02-22 | 102 |  |  | 100 | 2018-10-22 | 2019-02-22 | 2019-03-13 | 2019-07-16 | 170000 | 170000 | 0 | 170000 | 170000 | 1 | FALSE | Normal | FALSE | 2018-10-22 | 2019-02-22 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 170000 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1510 | Ultraviolet Sensor | Titan II Orbiter IMS | 67 | 67 | 2018-11-05 | 2019-02-05 | 115 |  |  | 113 | 2018-11-05 | 2019-02-05 | 2019-04-15 | 2019-07-16 | 140000 | 140000 | 0 | 140000 | 140000 | 1 | FALSE | Normal | FALSE | 2018-11-05 | 2019-02-05 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 67 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 140000 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1520 | Infrared Sensor | Titan II Orbiter IMS | 66 | 66 | 2018-11-19 | 2019-02-18 | 106 |  |  | 104 | 2018-11-19 | 2019-02-18 | 2019-04-16 | 2019-07-16 | 135000 | 135000 | 0 | 135000 | 135000 | 1 | FALSE | Normal | FALSE | 2018-11-19 | 2019-02-18 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 66 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 135000 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1110 | Software Installed | Titan II Orbiter IMS | 31 | 31 | 2018-12-20 | 2019-01-31 | 54 |  |  | 0 | 2018-12-20 | 2019-01-31 | 2019-03-06 | 2019-04-17 | 17360 | 17360 | 0 | 17360 | 17360 | 1 | FALSE | Normal | FALSE | 2018-12-20 | 2019-01-31 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 31 | 0 |  | Planned | 0% | 496 | 0 | 496 | 496 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.1.1.2.2.1.6 | Guidance Controls | 0 | 0 | 0 | 0 | 0 | 17360 | PercentComplete | 6% | CP_Phys | Percent Complete | Jackson | Engineering
FALSE |  | A1070 | Power Supply | Titan II Orbiter IMS | 35 | 35 | 2018-12-24 | 2019-02-08 | 69 |  |  | 0 | 2018-12-24 | 2019-02-08 | 2019-03-29 | 2019-05-16 | 90000 | 90000 | 0 | 90000 | 90000 | 2 | FALSE | Normal | FALSE | 2018-12-24 | 2019-02-08 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 0 |  | Planned | 0% | 1680 | 0 | 1680 | 1680 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.1 | Workshop Assembly | 0 | 0 | 0 | 0 | 0 | 90000 | PercentComplete | 6% | CP_Phys | 50/50 | Jackson | Engineering
FALSE |  | A1540 | Stereoscopic Camera | Titan II Orbiter IMS | 90 | 90 | 2018-12-31 | 2019-05-03 | 52 |  |  | 50 | 2018-12-31 | 2019-05-03 | 2019-03-13 | 2019-07-16 | 1 | 1 | 0 | 720 | 720 | 1 | FALSE | Normal | FALSE | 2018-12-31 | 2019-05-03 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 720 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1120 | Tested | Titan II Orbiter IMS | 29 | 29 | 2019-02-01 | 2019-03-13 | 54 |  |  | 0 | 2019-02-01 | 2019-03-13 | 2019-04-18 | 2019-05-28 | 40368 | 40368 | 0 | 40368 | 40368 | 2 | FALSE | Normal | FALSE | 2019-02-01 | 2019-03-13 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 29 | 0 |  | Planned | 0% | 928 | 0 | 928 | 928 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.1.1.2.2.1.6 | Guidance Controls | 0 | 0 | 0 | 0 | 0 | 40368 | PercentComplete | 6% | CP_Phys | Percent Complete | Jackson | Engineering
FALSE |  | A1080 | Solar Deployment Assembly | Titan II Orbiter IMS | 43 | 43 | 2019-02-11 | 2019-04-10 | 69 |  |  | 15 | 2019-02-11 | 2019-04-10 | 2019-05-17 | 2019-07-16 | 70720 | 70720 | 0 | 70720 | 70720 | 1 | FALSE | Normal | FALSE | 2019-02-11 | 2019-04-10 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 43 | 0 |  | Planned | 0% | 1032 | 0 | 1032 | 1032 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.1 | Workshop Assembly | 0 | 0 | 0 | 0 | 0 | 70720 | PercentComplete | 6% | CP_Phys | Percent Complete | Jackson | Engineering
FALSE |  | A1130 | Sign off | Titan II Orbiter IMS | 35 | 35 | 2019-03-14 | 2019-05-01 | 54 |  |  | 0 | 2019-03-14 | 2019-05-01 | 2019-05-29 | 2019-07-16 | 27206.67 | 27206.67 | 0 | 27206.6667 | 27206.6667 | 1 | FALSE | Normal | FALSE | 2019-03-14 | 2019-05-01 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 3 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 0 |  | Planned | 0% | 513.3333 | 0 | 513.3333 | 513.3333 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.1.1.2.2.1.6 | Guidance Controls | 0 | 0 | 0 | 0 | 0 | 27206.67 | PercentComplete | 6% | CP_Phys | Percent Complete | Jackson | Engineering
FALSE |  | A1170 | Install Sensor Instruments | Titan II Orbiter IMS | 3 | 3 | 2019-07-24 | 2019-07-26 | 114 |  |  | 114 | 2019-07-24 | 2019-07-26 | 2019-12-31 | 2020-01-02 | 107189 | 107189 | 0 | 107189 | 107189 | 1 | FALSE | Normal | FALSE | 2019-07-24 | 2019-07-26 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 0 |  | Planned | 0% | 96 | 0 | 96 | 96 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.2 | Clean Room Assembly | 0 | 0 | 0 | 0 | 0 | 107189 | PercentComplete | 6% | CP_Phys | Percent Complete |  | Engineering
FALSE |  | A1180 | Install Stereoscopic Cameras | Titan II Orbiter IMS | 9 | 9 | 2019-07-24 | 2019-08-05 | 108 |  |  | 108 | 2019-07-24 | 2019-08-05 | 2019-12-23 | 2020-01-02 | 65392 | 65392 | 0 | 65392 | 65392 | 1 | FALSE | Normal | FALSE | 2019-07-24 | 2019-08-05 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 9 | 0 |  | Planned | 0% | 216 | 0 | 216 | 216 | Titan II Orbiter IMS.1.1.2.1.2.2.1.2.2.2 | Clean Room Assembly | 0 | 0 | 0 | 0 | 0 | 65392 | PercentComplete | 6% | CP_Phys | Percent Complete |  | Engineering
8. High Duration
Total number of activities that have a duration longer than 2 months. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1350 | Program Management | Titan II Orbiter IMS | 666 | 666 | 2018-10-01 | 2021-04-19 | 0 |  |  | 0 | 2018-10-01 | 2021-04-19 | 2021-04-19 | 2021-04-19 | 903104 | 903104 | 0 | 0 | 0 | 0 | FALSE | Level of Effort | TRUE | 2018-10-01 | 2021-04-19 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3 | 7 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | LevelOfEffort | 666 | 0 |  | Planned | 0% | 18115.2 | 0 | 31968 | 31968 | Titan II Orbiter IMS.1.1.1 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Level of Effort | Jefferson | Mangement
FALSE |  | A1490 | Procurement | Titan II Orbiter IMS | 202 | 202 | 2018-10-08 | 2019-07-16 | 0 |  |  | 0 | 2018-10-08 | 2019-07-16 | 2019-07-16 | 2019-07-16 | 48640 | 48640 | 0 | 48640 | 48640 | 1 | FALSE | Level of Effort | TRUE | 2018-10-08 | 2019-07-16 |  |  | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | LevelOfEffort | 202 | 0 |  | Planned | 0% | 1616 | 0 | 1616 | 1616 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 48640 | PercentComplete | 6% | CP_Phys | Level of Effort | Jefferson | Mangement
FALSE |  | A1530 | RF Sensor | Titan II Orbiter IMS | 150 | 150 | 2018-12-17 | 2019-07-12 | 2 |  |  | 0 | 2018-12-17 | 2019-07-12 | 2018-12-19 | 2019-07-16 | 2 | 2 | 0 | 1200 | 1200 | 1 | FALSE | Normal | FALSE | 2018-12-17 | 2019-07-12 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 150 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 1200 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1540 | Stereoscopic Camera | Titan II Orbiter IMS | 90 | 90 | 2018-12-31 | 2019-05-03 | 52 |  |  | 50 | 2018-12-31 | 2019-05-03 | 2019-03-13 | 2019-07-16 | 1 | 1 | 0 | 720 | 720 | 1 | FALSE | Normal | FALSE | 2018-12-31 | 2019-05-03 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6.1.2.6.3 | Procure Science Instruments | 0 | 0 | 0 | 0 | 0 | 720 | PercentComplete | 6% | CP_Phys | Milestone | Lincoln | Procurement
FALSE |  | A1570 | Acquire Cabling | Titan II Orbiter IMS | 67 | 67 | 2019-02-11 | 2019-05-14 | 0 |  |  | 0 | 2019-02-11 | 2019-05-14 | 2019-02-11 | 2019-05-14 | 3000 | 3000 | 0 | 2999.9997 | 2999.9997 | 1 | FALSE | Normal | TRUE | 2019-02-11 | 2019-05-14 |  |  | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 67 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 3000 | PercentComplete | 6% | CP_Phys | Units Complete | Lincoln | Procurement
FALSE |  | A1580 | Assemble and Install Software | Titan II Orbiter IMS | 45 | 45 | 2019-05-15 | 2019-07-16 | 0 |  |  | 0 | 2019-05-15 | 2019-07-16 | 2019-05-15 | 2019-07-16 | 63000 | 63000 | 0 | 63000 | 63000 | 1 | FALSE | Normal | TRUE | 2019-05-15 | 2019-07-16 |  |  | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 45 | 0 |  | Planned | 0% | 1800 | 0 | 1800 | 1800 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 63000 | PercentComplete | 6% | CP_Phys | Units Complete | Lincoln | Procurement

## 2020 Details
Fuse® Analyst Report
Workbook: TITAN II ORBITER - 379 Activities
DCMA 14 Point
Created on: 9/15/2017
Created by: Neil
2020: Detailed View | 2020: Detailed View | 2020: Detailed View | 2020: Detailed View
4. SS/FF Relations
Number of Start to Start (SS) and Finish to Finish (FF) logic links. Should be lower than 10%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1330 | Sustained Vacuum High Voltage Ionization Testing | Titan II Orbiter IMS | 60 | 60 | 2020-01-03 | 2020-03-26 | 120 |  |  | 120 | 2020-01-03 | 2020-03-26 | 2020-06-19 | 2020-09-10 | 15360 | 15360 | 0 | 15360 | 15360 | 1 | FALSE | Normal | FALSE | 2020-01-03 | 2020-03-26 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 0 |  | Planned | 0% | 288 | 0 | 288 | 288 | Titan II Orbiter IMS.1.1.2.1.2.3 | Test | 0 | 0 | 0 | 0 | 0 | 15360 | PercentComplete | 6% | CP_Phys | 50/50 |  | Space Team
6. High Float
Number of activities with total float greater than 2 months. Should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1330 | Sustained Vacuum High Voltage Ionization Testing | Titan II Orbiter IMS | 60 | 60 | 2020-01-03 | 2020-03-26 | 120 |  |  | 120 | 2020-01-03 | 2020-03-26 | 2020-06-19 | 2020-09-10 | 15360 | 15360 | 0 | 15360 | 15360 | 1 | FALSE | Normal | FALSE | 2020-01-03 | 2020-03-26 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 0 |  | Planned | 0% | 288 | 0 | 288 | 288 | Titan II Orbiter IMS.1.1.2.1.2.3 | Test | 0 | 0 | 0 | 0 | 0 | 15360 | PercentComplete | 6% | CP_Phys | 50/50 |  | Space Team
FALSE |  | A1280 | Test Nitrogen Sensor | Titan II Orbiter IMS | 30 | 30 | 2020-01-03 | 2020-02-13 | 150 |  |  | 150 | 2020-01-03 | 2020-02-13 | 2020-07-31 | 2020-09-10 | 37440 | 37440 | 0 | 37440 | 37440 | 1 | FALSE | Normal | FALSE | 2020-01-03 | 2020-02-13 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 24 | 0 | 960 | 960 | Titan II Orbiter IMS.1.1.2.1.2.3.1.2.3.3 | Instrument Characterization | 0 | 0 | 0 | 0 | 0 | 37440 | PercentComplete | 6% | CP_Phys | Level of Effort |  | Space Team
FALSE |  | A1290 | Test Oxigen Sensor | Titan II Orbiter IMS | 30 | 30 | 2020-01-03 | 2020-02-13 | 150 |  |  | 150 | 2020-01-03 | 2020-02-13 | 2020-07-31 | 2020-09-10 | 37440 | 37440 | 0 | 37440 | 37440 | 1 | FALSE | Normal | FALSE | 2020-01-03 | 2020-02-13 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 24 | 0 | 960 | 960 | Titan II Orbiter IMS.1.1.2.1.2.3.1.2.3.3 | Instrument Characterization | 0 | 0 | 0 | 0 | 0 | 37440 | PercentComplete | 6% | CP_Phys | Level of Effort |  | Space Team
FALSE |  | A1300 | Test Hydrogen Sensor | Titan II Orbiter IMS | 30 | 30 | 2020-01-03 | 2020-02-13 | 150 |  |  | 150 | 2020-01-03 | 2020-02-13 | 2020-07-31 | 2020-09-10 | 37440 | 37440 | 0 | 37440 | 37440 | 1 | FALSE | Normal | FALSE | 2020-01-03 | 2020-02-13 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 24 | 0 | 960 | 960 | Titan II Orbiter IMS.1.1.2.1.2.3.1.2.3.3 | Instrument Characterization | 0 | 0 | 0 | 0 | 0 | 37440 | PercentComplete | 6% | CP_Phys | Level of Effort |  | Space Team
FALSE |  | A1310 | Test Helium Sensor | Titan II Orbiter IMS | 30 | 30 | 2020-01-03 | 2020-02-13 | 150 |  |  | 150 | 2020-01-03 | 2020-02-13 | 2020-07-31 | 2020-09-10 | 37440 | 37440 | 0 | 37440 | 37440 | 1 | FALSE | Normal | FALSE | 2020-01-03 | 2020-02-13 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 24 | 0 | 960 | 960 | Titan II Orbiter IMS.1.1.2.1.2.3.1.2.3.3 | Instrument Characterization | 0 | 0 | 0 | 0 | 0 | 37440 | PercentComplete | 6% | CP_Phys | Level of Effort |  | Space Team
FALSE |  | A1320 | Test Methane Sensor | Titan II Orbiter IMS | 30 | 30 | 2020-01-03 | 2020-02-13 | 150 |  |  | 150 | 2020-01-03 | 2020-02-13 | 2020-07-31 | 2020-09-10 | 37440 | 37440 | 0 | 37440 | 37440 | 1 | FALSE | Normal | FALSE | 2020-01-03 | 2020-02-13 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 24 | 0 | 960 | 960 | Titan II Orbiter IMS.1.1.2.1.2.3.1.2.3.3 | Instrument Characterization | 0 | 0 | 0 | 0 | 0 | 37440 | PercentComplete | 6% | CP_Phys | Level of Effort |  | Space Team
FALSE |  | A1590 | Solar Panels and Systems Parts | Titan II Orbiter IMS | 71 | 71 | 2020-09-11 | 2020-12-18 | 86 |  |  | 86 | 2020-09-11 | 2020-12-18 | 2021-01-11 | 2021-04-19 | 43744 | 43744 | 0 | 43744 | 43744 | 1 | FALSE | Normal | FALSE | 2020-09-11 | 2020-12-18 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 71 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 43744 | PercentComplete | 6% | CP_Phys | Planning Package | Lincoln | Procurement
8. High Duration
Total number of activities that have a duration longer than 2 months. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1350 | Program Management | Titan II Orbiter IMS | 666 | 666 | 2018-10-01 | 2021-04-19 | 0 |  |  | 0 | 2018-10-01 | 2021-04-19 | 2021-04-19 | 2021-04-19 | 903104 | 903104 | 0 | 0 | 0 | 0 | FALSE | Level of Effort | TRUE | 2018-10-01 | 2021-04-19 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3 | 7 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | LevelOfEffort | 666 | 0 |  | Planned | 0% | 18115.2 | 0 | 31968 | 31968 | Titan II Orbiter IMS.1.1.1 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Level of Effort | Jefferson | Mangement
FALSE |  | A1270 | Hydrazine Testing | Titan II Orbiter IMS | 180 | 180 | 2020-01-03 | 2020-09-10 | 0 |  |  | 0 | 2020-01-03 | 2020-09-10 | 2020-01-03 | 2020-09-10 | 74880 | 74880 | 0 | 74880 | 74880 | 2 | FALSE | Normal | TRUE | 2020-01-03 | 2020-09-10 |  |  | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 180 | 0 |  | Planned | 0% | 1440 | 0 | 1440 | 1440 | Titan II Orbiter IMS.1.1.2.1.2.3 | Test | 0 | 0 | 0 | 0 | 0 | 74880 | PercentComplete | 6% | CP_Phys | Percent Complete |  | Space Team
FALSE |  | A1330 | Sustained Vacuum High Voltage Ionization Testing | Titan II Orbiter IMS | 60 | 60 | 2020-01-03 | 2020-03-26 | 120 |  |  | 120 | 2020-01-03 | 2020-03-26 | 2020-06-19 | 2020-09-10 | 15360 | 15360 | 0 | 15360 | 15360 | 1 | FALSE | Normal | FALSE | 2020-01-03 | 2020-03-26 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 0 |  | Planned | 0% | 288 | 0 | 288 | 288 | Titan II Orbiter IMS.1.1.2.1.2.3 | Test | 0 | 0 | 0 | 0 | 0 | 15360 | PercentComplete | 6% | CP_Phys | 50/50 |  | Space Team
FALSE |  | A1590 | Solar Panels and Systems Parts | Titan II Orbiter IMS | 71 | 71 | 2020-09-11 | 2020-12-18 | 86 |  |  | 86 | 2020-09-11 | 2020-12-18 | 2021-01-11 | 2021-04-19 | 43744 | 43744 | 0 | 43744 | 43744 | 1 | FALSE | Normal | FALSE | 2020-09-11 | 2020-12-18 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 71 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | Titan II Orbiter IMS.1.1.2.1.2.6 | Materials | 0 | 0 | 0 | 0 | 0 | 43744 | PercentComplete | 6% | CP_Phys | Planning Package | Lincoln | Procurement

## 2021 Details
Fuse® Analyst Report
Workbook: TITAN II ORBITER - 379 Activities
DCMA 14 Point
Created on: 9/15/2017
Created by: Neil
2021: Detailed View | 2021: Detailed View
8. High Duration
Total number of activities that have a duration longer than 2 months. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | EVT | CAM | OBS
FALSE |  | A1350 | Program Management | Titan II Orbiter IMS | 666 | 666 | 2018-10-01 | 2021-04-19 | 0 |  |  | 0 | 2018-10-01 | 2021-04-19 | 2021-04-19 | 2021-04-19 | 903104 | 903104 | 0 | 0 | 0 | 0 | FALSE | Level of Effort | TRUE | 2018-10-01 | 2021-04-19 |  |  | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3 | 7 |  |  |  |  | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | LevelOfEffort | 666 | 0 |  | Planned | 0% | 18115.2 | 0 | 31968 | 31968 | Titan II Orbiter IMS.1.1.1 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Level of Effort | Jefferson | Mangement