## Sheet1
Projects Pane Column Definitions
Column | Desription
% Complete | Displays the percentage of the work that has been completed, which is calculated using the formula Earned/BAC * 100.
% Spent | Displays the percentage of the budget spent, which is calculated using the formula (Actual/EAC) * 100.
Actual Finish | Displays the actual finish date of the project.
Actual Rate | Displays the actual rate, calculated using the formula Actual/Actual.Hours.
Actuals | Displays the total actual currency value of project. The Update Totals utility populates the value in the table.
Address | Displays the address of the contractor.
AUW | Displays the amount of any Authorized Unpriced Work (AUW) for the project.
BAC | Displays the budget at completion or the resource total.
Baseline Finish | Displays the baseline finish date that defines the last date of the project.
Baseline Start | Displays the baseline start date that defines the initial status date for the project.
Baselined | Indicates whether the project audit log has been turned on to set the baseline for the project.
Batch No. | Displays the batch number that is stored in the tphase and the project audit log. Each time a process is run, the batch number is incremented.
Best Case EAC | Displays the Estimated Cost at Completion (EAC) value for best-case forecasts displayed in the header of the CPR reports. Use the Budget tab of the Project Properties dialog box to enter this value.
Budget | Displays the total currency budget value of project. The Update Totals utility populates the value in the table.
Budget Rate | Displays the budget rate, calculated using the formula Budget to Date/Budget to Date Hours.
Ca[1-3] Code File | Displays the code files assigned to the control account.
Ca[1-3] Key Term | Displays the prompt that represents the code field.
Calendar File | Displays the calendar file used in the project.
CAM Code Field No. | Displays the CAM code field number.
Capture Actuals Level | Displays the level at which you want to capture actual costs (Control Account, Work Package, or both Control Account and Work Package).
CBB | Displays the Contract Budget Base (CBB) for the project, which is the combined Negotiated Cost and AUW.
Ceiling | Displays the Budgeted and Estimate at Complete Contract Ceiling amounts for the project.
CCN Code File | Displays the code file validating the change number.
CCN Use Code File | Indicates whether there is a file validating the change number.
CCN Validation | Displays the validation type.
Classification | Displays the security classification of the contract, which is displayed on the top and bottom of the CPR reports.
Complete | Indicates that the project is already complete.
Contract Name | Displays the name of the contract.
Contract Flag | Displays the contract type.
Contract Number | Displays the contract number.
Contract Phase | Displays the project phase.
Contract Representative Name | Displays the name of the person assigned to the contract.
Contract Representative Title | Displays the title of the representative assigned to the contract.
Contract Type | Displays the contract type, such as CPFF (Cost Plus Fixed Fee).
Contract Location | Displays the location of the contractor.
Contractor Name | Displays the contractor name, which is used on Cobra reports.
CostProject.EvmsAcceptanceId | Indicates that the project passed EVMS validation. This is displayed in the header of the CPR reports. Use the Project Properties dialog box to edit the contents of this field.
CostPrject.IpmrFormat2Code | Indicates that the IPMR Format 2 report uses an alternate code field.
CostProjecct.ProductVisibility | Indicates that the project is visible in PM Compass.
CPI | Displays the Cost Performance Index, which is calculated using the formula Earned/Actual.
CPI Performance | Displays the CPI performance of the project, which is calculated using the formula Actual/Earned.
CTC | Displays the cost for the contract and all authorized changes as of a specific date. This amount usually includes any management reserves.
Currency Symbol | Displays the currency symbol to be used to display costs in the Projects view and the Explorer view (for example, $ for dollars and € for Euros).
Currency Symbol on Right? | Indicates whether the currency abbreviation (such as USD) is displayed to the right of any currency value.
CV | Displays the Cost Variance, which is calculated using the formula Earned - Actual.
CV % | Displays the Cost Variance percentage, which is calculated using the formula (Earned - Actual)/Earned *100.
Definite | Displays the date the contract was made definite.
Description | Displays a brief description of the project, control account, or work package.
EAC | Displays the total Estimate At Complete currency value of the project based on the cost set EAC. The Update Totals utility populates the value in the table.
Earned | Displays the total earned currency value of the project. The Update Totals utility populates the value in the table.
Est. Ceiling | Displays the estimated ceiling amount for the project. This is displayed on CPR reports and can be edited in the Project Properties dialog box.
Est. MR | Displays the estimated management reserve cost for the project. This is displayed on CPR reports and can be edited in the Project Properties dialog box.
Est. UB | Displays the estimated undistributed budget for the project. This is displayed on CPR reports and can be edited in the Project Properties dialog box.
Estimated Price | Displays the estimated Contract Target Price at the completion of the project. This is the sum of the Contract Budget Base and any management fees. This is displayed on CPR reports and can be edited in the Project Properties dialog box.
EVMS Acceptance Date | Displays the approval or disapproval date of the Earned Value Management System (EVMS) for the project. This is displayed on CPR reports and can be edited in the Project Properties dialog box.
Fee | Displays the management fee for the project. This is displayed on CPR reports and can be edited in the Project Properties dialog box.
Fee Percent | Displays the management fee for the project, expressed as a percentage of the Contract Budget Baseline.
Forecast Finish | Displays the latest forecast finish date of the project.
Forecast Method Range 1 - 4 | Displays the forecast methods used for the class.
Hours % Complete | Displays the percentage of the work that has been completed, calculated using the formula Earned Hours/BAC Hours * 100.
Hours % Spent | Displays the percentage of the budget spent, which is calculated using the formula (Actual Hours/EAC Hours) * 100.
Hours Actuals | Displays the total actual currency value of the project, which is calculated using the formula (Actual Hours/EAC Hours) * 100.
Hours BAC | Displays the budget at completion in hours.
Hours Budget | Displays the budget to date in hours.
Hours CPI | Displays the Cost Performance Index, which is calculated using the formula Earned Hours/Actual Hours.
Hours CPI Performance | Displays the CPI performance of the project, which is calculated using the using the formula Actual Hours/Earned Hours.
Hours CV | Displays the Cost Variance, which is calculated using the formula Earned Hours - Actual Hours.
Hours CV % | Displays the Cost Variance percentage, which is calculated using the formula CV Hours/Earned Hours * 100.
Hours EAC | Displays the total Estimate At Complete currency value of the project in hours.
Hours Earned | Displays the total earned currency value of project hours.
Hours iEAC | Displays the independent Estimate At Complete, which is calculated using the formula 1/CPI (Budget at Complete Hours - Earned Hours) + Actual Hours.
Hours EAC2 | Displays the independent Estimate At Complete, which is calculated using the formula 1/CPI *SPI (BAC Hours- Earned Hours) + Actual Hours.
Hours SPI | Displays the Schedule Performance Index (SPI), which is calculated using the formula Earned Hours /Budget to Date Hours.
Hours SV | Displays the Schedule Variance (SV), which is calculated using the formula Earned Hours - Budget to Date Hours.
Hours SV % | Displays the Schedule Variance (SV) percentage, which is calculated using the formula SV Hours/Earned Hours *100.
Hours TCPI | Displays the To Complete Performance Index (TCPI), which is calculated using the formula (BAC Hours - Earned Hours)/ (EAC Hours — Actual Hours).
Hours TCPI BAC | Displays the To Complete Performance Index within the project budget at complete, which is calculated using the formula (BAC Hours — Earned Hours)/ (BAC Hours - Actual Hours).
Hours VAC | Displays the Variance At Complete (VAC), which is calculated using the formula BAC Hours - EAC Hours.
Hours VAC % | Displays the Variance At Complete (VAC) percentage, which is calculated using the formula (BAC Hours - EAC Hours)/ BAC Hours*100.
Hours Variance | Displays the Variance, which is calculated using the formula Budget at Complete Hours - Forecast at Complete Hours.
iEAC | Displays the independent Estimate At Complete, which is calculated using the formula Actual + [1/ CPI(BAC - Earned)].
iEAC2 | Displays the independent Estimate at Complete, which is calculated using the formula Actual + [1/ (CPI*SPI)(BAC - Earned)].
Last Updated | Displays the date when the project details were last updated.
LRE | Displays the Latest Revised Estimate At Completion (LRE), which is the updated and most recent Estimate at Completion (EAC).
Manager Code File | Displays the code file validating the manager (CAM) code.
Manager Code File Type | Displays the code file type validating the manager CAM code.
Manager Validation | Indicates that there is a code file validating the manager.
Master Project Flag | Indicates that the project is a master project.
MPS CODE | Displays the project level in the database.
MR | Displays the budgeted and estimated final management reserve for the project.
Open Plan Project | Displays the Open Plan project used by the Cobra project.
OTB | Displays the baseline which results from formal reprojecting of an overrun, used only with the approval of the customer.
OTB Date | Displays the date when OTB was allocated to the project.
OTC | Displays the Original Negotiated Cost value.
Percent Range 1 – 3 | Displays the range used for the forecast method. The range varies based on % Complete.
Period Start Date | Displays the previous status date used in report headers.
Project | Displays the name of the project.
Project Code 1 - 9 | Displays the project level codes for the project.
Quantity | Displays the number of items to be procured for the contract.
Rate File | Displays the rate file used for the project.
Resource Code File | Displays the resource code file used for the project.
Resource Key Term | Displays the resource field name.
Resource File | Displays the resource file used for the project.
Rolling Wave Calendar | Displays the rolling wave calendar used for the project.
Scale Caption | Displays the caption for the scale factor that appears in the reports.
Scale Factor | Displays the scale factor that will be used to report currency amounts.
Sequence | This field is used internally by Cobra.
Share Ratio | Displays the share ratio for the contract.
SPI | Displays the Schedule Performance Index, which is calculated using the formula Earned/Budget to Date.
Spread Weight Method | Displays the spread weight method.
State | Displays the state where the contractor is located.
Status Date | Displays the status date of the project.
SV | Displays the Schedule Variance, which is calculated using the formula Earned - Budget to Date.
SV % | Displays the Schedule Variance percentage, calculated using the formula (Earned - Budget to date)/Budget to date * 100.
Target Price | Displays the estimated Contract Target Price at the completion of the project. This is the sum of the Contract Budget Base and any management fees.
TCPI | Displays the To Complete Performance index, which is calculated using the formula (BAC - Earned)/ (EAC - Actual).
TCPI BAC | Displays the To Complete Performance index within the project budget at complete, which is calculated using the formula (BAC-Earned)/(BAC-Actual).
UB | Displays the Undistributed Budget. This is the budget applicable to contract effort which has not yet been identified to Contract Work Breakdown Structure (CWBS) elements at or below the lowest level of reporting to the government.
User | Displays the individual who is currently accessing the project.
VAC | Displays the Variance At Complete, which is calculated using the formula BAC - EAC.
VAC % | Displays the Variance At Complete percentage, which is calculated using the formula (BAC - EAC)/ BAC*100.
Variance | Displays the Variance, which is calculated using the formula Budget at Complete - Forecast at Complete.
Worst Case EAC | Displays the Estimated Cost at Completion (EAC) value for worst-case forecasts. Use the Budget tab of the Project Properties dialog box to enter this value.
Wp Code File | Displays the work package code file assigned to the project.
Wp Key Term | Displays the work package field name.
Zip | Displays the zip code where the contractor is located.
Spreadsheet Pane Column Definitions
Column | Description
% Spent | Displays the percentage of the forecast spent, which is calculated using the formula (Actual/EAC) * 100.
Actual Finish | Displays the actual finish date of the control account or work package.
Actual Rate | Displays the actual rate, which is calculated using the formula Actual/Actual.Hours.
Actual Start | Displays the actual start date of the control account or work package.
Actuals | Displays the total actual currency value of the control account or work package. The Update Totals utility populates the value in the table.
Apportioned CaWP Uid | Displays the UID for the work package stored in the Apportioned to field.
Apportioned to | Displays the work package to which the budget for the referenced work package is apportioned.
Assignment % Complete | Displays the percentage of work that has been completed for the Earned Value class to which the resource is assigned.
BAC | Displays the budget at completion or the resource total.
Baseline Finish | Displays the baseline finish date that defines the last date of the control account or work package.
Baseline Start | Displays the baseline start date that defines the initial status date for the control account or work package.
Budget | Displays the total currency budget value of the control account or work package. The Update Totals utility populates the value in the column.
Budget Rate | Displays the budget rate, which is calculated using the formula Budget to Date/Budget to Date Hours.
Ca[1-3]Id | Displays the control account field names.
Calculated % Complete | Displays the percentage of the work that has been completed, which is calculated using the formula Earned/BAC * 100. The value in the column is populated when you run the Calculate Progress process or when you manually edit or create the Earned Value class of a resource assignment and run the Update Totals process.
CAM | Displays the Control Account Manager (CAM) code attached to the control account.
CaWpUid | This is used internally by Cobra.
CI Batch | This is used internally by Cobra.
Class | Displays the class associated with the resource.
Class Description | Displays a brief description of the class associated with the resource.
Control Account Codes [1-9] | Displays the control account codes.
CPI | Displays the Cost Performance Index, which is calculated using the formula Earned/Actual.
CPI Performance | Displays the CPI Performance, which is calculated using the formula Actual/Earned.
Current Period Actuals | Displays the current period actual currency value of the control account or work package. The Update Totals utility populates the value in the table.
Current Period Budget | Displays the current period budget value of the control account or work package. The Update Totals utility populates the value in the table.
Current Period Hours Actuals | Displays the current period actuals value in hours of the control account or work package. The Update Totals utility populates the value in the table.
Current Period Hours Budget | Displays the current period budget value in hours of the control account or work package. The Update Totals utility populates the value in the table.
Current Period Hours Progress | Displays the current period earned value in hours of the control account or work package. The Update Totals utility populates the value in the table.
Current Period Progress | Displays the current period earned value of the control account or work package. The Update Totals utility populates the value in the table.
CV | Displays the Cost Variance, which is calculated using the formula Earned - Actual.
CV % | Displays the Cost Variance percentage, which is calculated using the formula CV/Earned * 100.
Description | Displays a brief description of the control account or work package.
EAC | Displays the total Estimate At Complete currency value based on the cost set EAC. The Update Totals utility populates the value in the table.
Early Finish | Displays the early finish date for the control account or work package.
Early Start | Displays the early start date for the control account or work package.
Forecast Finish | Displays the forecast finish date of the control account or work package.
Forecast Start | Displays the initial status date for the control account or work package.
Hours % Complete | Displays the percentage of the work that has been completed, calculated using the formula Earned Hours/BAC Hours * 100.
Hours % Spent | Displays the percentage of the budget spent, which is calculated using the formula (Actual Hours/EAC Hours) * 100.
Hours Actuals | Displays the total actual currency value, which is calculated using the formula (Actual Hours/EAC Hours) * 100.
Hours BAC | Displays the budget at completion in hours.
Hours Budget | Displays the budget to date values in hours.
Hours CPI | Displays the Cost Performance Index, which is calculated using the formula Earned Hours/Actual Hours.
Hours CPI Performance | Displays the CPI Performance, which is calculated using the formula Actual Hours/Earned Hours.
Hours CV | Displays the Cost Variance, which is calculated using the formula Earned Hours - Actual Hours.
Hours CV % | Displays the Cost Variance percentage, which is calculated using the formula CV Hours/Earned Hours * 100.
Hours EAC | Displays the total Estimate At Complete currency value in hours.
Hours iEac | Displays the independent Estimate At Complete, which is calculated using the formula 1/CPI (Budget at Complete Hours - Earned Hours) + Actual Hours.
Hours iEac2 | Displays the independent Estimate At Complete, which is calculated using the formula 1/CPI *SPI (BAC Hours- Earned Hours) + Actual Hours.
Hours Progress | Displays the total earned currency value in hours.
Hours SPI | Displays the Schedule Performance Index (SPI), which is calculated using the formula Earned Hours /Budget to Date Hours.
Hours SV | Displays the Schedule Variance (SV), which is calculated using the formula Earned Hours - Budget to Date Hours.
Hours SV % | Displays the Schedule Variance (SV) percentage, which is calculated using the formula SV Hours/Earned Hours *100.
Hours TCPIbac | Displays the To Complete Performance Index for the budget at complete, which is calculated using the formula (BAC Hours - Earned Hours)/ (BAC Hours - Actual Hours).
Hours TCPIeac | Displays the To Complete Performance Index for the projected estimate at complete, which is calculated using the formula (BAC Hours - Earned Hours)/ (EAC Hours - Actual Hours).
Hours VAC | Displays the Variance At Complete (VAC), which is calculated using the formula BAC Hours - EAC Hours.
Hours VAC % | Displays the Variance At Complete (VAC) percentage, which is calculated using the formula (BAC Hours - EAC Hours)/ BAC Hours*100.
Hours Variance | Displays the Variance, which is calculated using the formula Budget at Complete Hours - Forecast at Complete Hours.
iEac | Displays the independent Estimate At Complete, which is calculated using the formula Actual + [1/ CPI(BAC - Earned)].
iEac2 | Displays the independent Estimate at Complete, which is calculated using the formula Actual + [1/ (CPI*SPI)(BAC - Earned)].
Last Update | Displays the date when the control account or work package details were last updated.
Late Finish | Displays the late finish date for the control account or work package.
Late Start | Displays the late start date for the control account or work package.
Non Labor EAC | Displays the EAC value for resources that do not have an hours result. This field is used in the scale EAC currency option when both hours and currency are selected.
Op Batch | This is used internally Cobra.
Pending Finish | Displays the pending finish date of the control account or work package.
Pending Start | Displays the pending start date of the control account or work package.
Percent Complete | Displays the manually entered percent complete used to calculate earned value for work packages with a progress technique of Percent Complete.
Performance Factor | Displays the performance factor value, usually based on performance to date, which is divided into the budgeted cost of work remaining to arrive at an Estimate To Complete (ETC).
Progress | Displays the total earned currency value of the control account or work package. The Update Totals utility populates the value in the table.
Progress Technique | Displays the progress technique assigned to the work package.
Project | Displays the name of the project.
Resource | Displays resource assignment for the selected cost set or class type.
Resource Assignment Codes [1-9] | Displays resource assignment codes.
Resource Description | Displays a brief description of the resource.
Sequence | This column is used internally by Cobra.
SPI | Displays the Schedule Performance Index, which is calculated using the formula Earned/Budget to Date.
Spread Curve | Displays the spread curve name for the budget or forecast resource assignments. If there is no assigned spread curve, or if the resource assignment is manually spread or adjusted, Displays Manual.
For other types of resource assignments, this column is blank.
Start Percent | Displays the opening percent complete for work packages that use the user-defined progress technique.
Status | Displays the status of the selected control account or work package.
SV | Displays the Schedule Variance, which is calculated using the formula Earned - Budget to Date.
SV % | Displays the Schedule Variance percentage, which is calculated using the formula SV/Earned *100.
TCPIbac | Displays the To Complete performance index for the budget at complete, which is calculated using the formula (BAC-Earned)/(BAC-Actual).
TCPIeac | Displays the To Complete Performance Index for the projected estimate at complete, which is calculated using the formula (BAC - Earned)/ (EAC-Actual).
Total | Displays the current total for each of the results over the life of the project.
Uid | Displays the unique ID for the row.
Units | Displays how the result is measured. For example, a unit of measurement might be dollars, or it might be tons.
Units Complete | Displays the number of units completed.
Units To Do | Displays the number of units that remain to be completed, which is available only if you selected the Units Complete progress technique.
User | Displays the individual who is currently accessing the project, which is available only if you selected the Units Complete progress technique.
User Character Fields [1-10] | Displays the character fields that can be used for display in the view, or can be added as tags in the reports.
Note: You must first run the required script to display User Character Fields [6-10]. Refer to “Appendix E: Configure Cobra to Support Additional User Fields” of the Deltek Cobra 8.2 Installation Guide for instructions on how to configure Cobra to use these additional fields.
User Date Fields [1-10] | Displays the date fields that can be used for display in the view, or can be added as tags in the reports.
Note: You must first run the required script to display User Date Fields [6-10]. Refer to “Appendix E: Configure Cobra to Support Additional User Fields” of the Deltek Cobra 8.2 Installation Guide for instructions on how to configure Cobra to use these additional fields.
User Numeric Fields [1-10] | Displays the numeric fields that can be used for display in the view, or can be added as tags in the reports.
Note: You must first run the required script to display User Numeric Fields [6-10]. Refer to “Appendix E: Configure Cobra to Support Additional User Fields” of the Deltek Cobra 8.2 Installation Guide for instructions on how to configure Cobra to use these additional fields.
VAC | Displays the Variance At Complete, which is calculated using the formula BAC - EAC.
VAC % | Displays the Variance At Complete percentage, which is calculated using the formula (BAC - EAC)/ BAC*100.
Variance | Displays the Variance, which is calculated using the formula Budget at Complete - Forecast at Complete.
Work Package | Displays the work package ID.
Work Package Codes [1-9] | Displays the work package codes assigned to the project.
Work Package Manager | Displays the work package manager assigned to the project.